## Sheet1
Installation Worksheet | [5 empty] | Install Workbreakdown | [20 empty] | Enter Order Dates From All Suppliers Below
Contract Detail | [5 empty] | Salesperson Responsibilities | [6 empty] | Help Desk Responsibilities | [11 empty] | Logistics Detail
Account | Rep | Contract Date | Install Date | Deposit | Balance | Install Requirements Received? | BSQ Page 1 Received? | Exhibit D Received via Email? | Full BSQ Received? | Sample Menu Received? | CC Processor Info | Dialup Info Received? | Acct Created | Support Contract | INI & LIC | Database copied from another store? | Test Dialup | CC Authorized by Joel or Acct Rep? | CC DAT Created and Uploaded | Customer Data Authorized by Joel or Acct Rep | Customer Data Created and Uploaded | Menu Created | TS Lics Installed | Notes | Installer | Travel | Seneca | Blue Star | Ofc Depot | TekVisions | Other Supp
The Vault | GA |  | 2004-05-03 | 38500 | 7288 |  |  | Yes |  |  |  |  | Done | Done |  | ? |  | JO |  | N/A | N/A | ? |  |  | RM&JA | 2004-04-16 | 2004-04-19 | 2004-04-19 |  | 2004-04-19
Woodstock - Davis | SB | 2004-04-05 | 2004-05-06 | 6954 | 0 | [19 empty] | RM | 2004-04-16 | 2004-04-20 | na | na | na
Jet's Lake Orient | SB | 2004-01-30 | 2004-05-07 | 5000 | 13500 | No | Yes | Yes |  |  |  |  | Done | Done |  | in Van |  | JO |  | JO | WIP |  |  |  |  | Adam Drive | 2004-05-03 | 2004-05-03 | na | 2004-05-03
Pizza Inn - Morristown (Hill) | GA | 2004-03-26 | 2004-05-10 | 11445 | 0
Pizza Inn - Jefferson City (Hill) | GA | 2004-03-26 | 2004-05-10 | 11445 | 0
Anchor Bar | GA | 2004-03-26 | 2004-05-07 | 5997 | 5997
Pizza Inn Willis | GA | 2004-04-20 | 2004-05-07 | 3200 | 3184
Christos | G/F |  | 2004-05-10 | 7145 | 4765 |  | ? | Yes | ? |  | N/A |  | Done | Done |  | ? |  | N/A | N/A |  |  | ?
Island Pizza - Monteo | GA | 2004-03-29 | 2004-05-15 | 9786 | 9784
Stone Oven | GA |  | 2004-05-15 | 0 | 0
Pizza Inn - Truman | GA | 2004-03-26 | 2004-05-17 | 5000 | 7833
Hungry Howie's - Hillsdale (Hershock) | AG | 2004-03-31 | 2004-05-17 | 13420 | 0
Hungry Howie's - Charlotte (Jobson) | AG | 2004-04-27 | 2004-05-17 | 7485 | 7485
Hungry Howie's - Columbus | AG | NA | 2004-05-17 | 0 | 0
Rocky Roccoco's (2 Stores) | AG | 2004-04-27 | 2004-05-24 | 13565 | 13565
Bottle Shop | FC | 2004-03-20 | 2004-05-24 | 6700 | 6700 |  | ? | Yes | ? | ? |  |  | Done | Done |  | ? |  |  |  | N/A | N/A | ? | N/A | peer to peer
Hungry Howie's - Laredo Calypso | AG | 2004-02-27 |  | 6900 | 6977 |  |  | Fax |  |  |  |  | Done | Done |  | ? |  | JO |  | JO |  | ?
Pizza Lover - Antioch | GA | 2004-03-26 |  | 500 | 4279
Pizza Man | SB | 2004-03-17 |  | 4150 | 3350 | [18 empty] | Need Exhibit D
Burger Joe's | FC | 2004-04-20 |  | 1644 | 14800
Four Seasons | FC | 2004-04-20 |  | 1298 | 11685
Hungry Howie's - St Johns (Dittrich) | AG |  |  | 9029 | 0
Pizza Masters - Aliquippa #2 | GA | 2004-04-22 |  | 0 | 13700
Avanti's | FC | 2004-04-20 | Web | 3475 | 0
|  | Today: | 2004-05-04 | 172638 | 134892
Recent Installs that still need info or are not fully complete:
Hungry Howie's - Jacksonville | AG | 2004-03-08 | 2004-04-26 | 15284 | 0 | [10 empty] | ? |  | ? | ? | ? | ? | ? | ? |  | MA |  | 2004-04-19 | 2004-04-19 |  | 2004-04-19
Pizza Sam's | GA |  | 2004-04-26 | 8000 | 8530 |  | ? | Fax | ? |  |  |  | Done | Done |  | ? |  | JO |  | JO |  | ? |  | 20,000 Zips | AG&JO | 2004-04-16 | 2004-04-19 | 2004-04-19 |  | 2004-04-19
House of Pizza - St. Cloud #2 Testa | GA | 2003-11-26 | 2004-04-13 | 18000 | 18000 |  | Yes | Yes |  | N/A | [5 empty] | WIP |  | JO |  | JO |  |  |  | waiting for payment | RM&MA | 2004-04-05 | 2004-04-02 | 2004-04-02 | 2004-04-02 | 2004-04-02 | 4/01 - Dell
Pacific Wok - St. Cloud #2 Testa | GA | 2003-11-26 | 2004-04-13 | 0 | 0 |  | N/A | Yes | Yes | Yes | [5 empty] | N/A |  | JO |  | JO |  |  |  | waiting for payment | RM&MA
Jimmy's Pizza | SB | 2004-01-20 | 2004-03-22 | 13300 | 0 |  | Yes | Yes |  |  | NA |  | Done | Done | on FTP | on FTP |  | N/A | N/A | JO | WIP | ? |  |  | MA | Booked | 2004-03-18 | 2004-03-18 | 2004-03-22 | 2004-03-18
Pizza Masters - Aliquippa | GA | 2003-10-28 | 2004-03-15 | 15997 | 0 | No | Yes | Yes | Yes | Yes | Yes | Yes | Done | Done | on FTP | N/A | Done | Yes | on FTP | Yes | on FTP | on FTP | Done |  |  |  | 2004-03-08 | 2004-03-08 |  | 2004-03-08 | 2004-03-08
Hungry Howie's - Noblesville (Chad) | AG | N/A | 2004-03-08 | 16844 | 0 | No | No | Yes | Yes |  | WIP | Yes | Done | Done | Done | RM | Done | JO |  | JO | Done | N/A | Done
Pizza King #2 1909 Walnut, Bloomington | GA |  | Dec 2003 | 7375 | 3375 | No | No | No |  |  |  |  | Done | Done | [5 empty] | N/A | N/A | N/A | on FTP | One of the checks bounced
Sub Shop | VV | 2004-02-02 | 2004-02-19 | 7200 | 0 | [5 empty] | WIP |  | Done | Done | Done | N/A |  | Yes |  | N/A | N/A | Yes | N/A | Wireless | Val/Joel
Hungry Howie's - 805 Elyria, Shuckman | SB |  |  | 8571 | 0 |  |  | Fax |  |  | N/A |  | Done | Done | Done | ? |  | N/A | N/A | N/A | N/A | ? | N/A | Server only
Fully Completed:
Big Slice Pizza | GA |  | 2004-04-08 | 14989 | 0 |  | ? | Yes | ? |  |  |  | Done | Done |  | ? |  | JO |  | N/A | N/A | ? |  |  | RM | 2004-03-31 | 2004-03-31 | 2004-03-31 | 2004-04-05 | 2004-03-31 | 2004-03-31
Defelice Bro's | GA |  | NA | 4335 | 0 |  | Yes | Yes | N/A | N/A | N/A |  | Done | Done |  | Done |  | N/A | N/A | JO |  | N/A | N/A | Software only
Hungry Howie's - Dawoodjee 1000 Oaks | AG |  | 2004-01-30 | 14990 | 0 | No | No | No |  |  | Yes | Yes | Done | Done | AG | AG | Done | Yes | Done | AG | Done | N/A | Done | Adam is acting proj. mgr.
Pizza Inn - Jonesboro, Ark | GA | 2003-12-09 | 2004-02-18 | 19000 | 0 | Yes | Yes | No | Yes |  | N/A | Yes | Done | Done | Done | Done | Done | N/A | N/A | GA | Done | N/A | Done | Do we need to modify the menu? | Marq?
Hungry Howie's - Lake Mary #103 Wei Huang | AG | 2004-01-06 | 2004-02-09 | 17827 | 0 | No | No | Yes | Yes | Yes | Yes | Yes | Done | Done | AG | Done | Done | JO | Done | JO | Done | SK | Done | do we need to copy and modify an existing menu? | Ray | 2004-02-02 | 2004-02-02 | 2004-02-02 | 2004-02-02 | 2004-02-02
Jet's - Birmingham MI | SB | 2004-02-02 | 2004-02-10 | 11845 | 0 | Yes | Yes | Yes | N/A | N/A | N/A | Yes | Done | Done | AG | Done | Done | N/A | N/A | JO | Done | N/A | Done | 11th hour. Info needed for Support | Adam/AW | NA | 2004-02-03 | 2004-02-03 | 2004-02-03 | 2004-02-03
Jet's Lincoln Park - Gibson | SB |  | Jan 2004 | 14692 | 888 | No | No | No |  |  |  | Yes | Done | Done | Yes | Yes | Done |  |  |  |  | N/A | Done
Hungry Howie's - 831 Toledo - Pat Shannon | AG | 2004-01-01 | 2004-01-27 | 17823 | 0 | No | No | Yes |  |  | Yes | Yes | Done | Done | N/A | N/A | Done | Yes | Done | AG | Done | N/A | N/A | peer to peer | Adam
Pizza Inn - Conroe #3 | GA | 2004-01-12 | 2004-01-29 | 3200 | 164 | No | No | Yes | No |  | N/A | Yes | Done | Done | Yes | N/A | Done | N/A | N/A | LO | Done | N/A | N/A |  | Marquette
Daddio's | VV | 2004-01-16 | ASAP | 6000 | 0 | No | No | Yes |  |  | Yes | Yes | Done | Done | Yes | N/A | Done | JO | Done | N/A | N/A | Done | N/A | Val is acting proj. mgr. | Val | NA
Big Apple - Pt. St. Lucie (Savage) | GA | 2004-01-02 | 2004-02-01 | 12286 | 0 | No | No | No |  |  |  | Yes | Done | Done | Yes | [7 empty] | Done | 3 lics | Marquette | NA | 2004-02-02 | 2004-02-02 | 2004-02-02 | 2004-02-02
Kevin's edits are in Blue
Items that need to be done in order to get paid by the customer!
GL - Go Leads
WIP - work in process
AW - Allen Winkle
Note on D14: Joel: No Install. Hardware only.
Note on D17: Joel: Maintenance Only