## Sheet1
Tasks for building project | Day number | Scheduled Date | reference date | Actual Date | DOW | Name of work crew | Date
Apply for building permit | 1 | 2004-03-09 |  | 2004-03-09 | Tuesday | ED
Building permit approved | 2 | 2004-03-15 |  | 2004-04-13 | Tuesday | City Inspector
Dig basement | 3 | 2004-04-14 |  | 2004-04-14 | Wednesday | contracted
set forms | 4 | 2004-04-16 |  | 2004-04-17 | Saturday | individuals
Request pre-concrete inspection | 5 | 2004-04-16 |  | 2004-04-19 | Monday | Construction Manager
Footing forms inspection |  |  |  | 2004-04-20 | Tuesday | Construction Manager
pour footings | 6 | 2004-04-16 |  | 2004-04-20 | Tuesday | individuals
Lay Ice Block forms | 7 | 2004-04-17 | 2004-04-24 | 2004-04-24 | Saturday | Workforce Development - Youth Builds
Lay Ice Block forms | 8 | 2004-04-27 | 2004-04-27 | 2004-04-27 | Tuesday | individuals
Lay Ice Block forms | 9 | 2004-04-28 | 2004-04-28 | 2004-04-28 | Wednesday | individuals
Lay Ice Block forms | 10 | 2004-04-29 | 2004-04-29 | 2004-04-29 | Thursday | individuals
Foundation Wall Inspection |  |  |  | 2004-04-29 | Thursday | Construction Manager
Pour walls | 11 | 2004-04-30 | 2004-04-30 | 2004-04-30 | Friday | individuals
Apply waterproofing, Frame basement bearing wall | 12 | 2004-05-01 | 2004-05-01 | 2004-05-01 | Saturday | individuals
Stub water / sewer to curb | 13 | 2004-05-03 | 2004-05-03 | 2004-05-03 | Monday | City of Red Wing
water/sewer service inspection |  |  |  | 2004-05-04 | Tuesday | Construction Manager
Set floor joists, Frame basement bearing wall, frame & pour stairway footing | 14 | 2004-05-04 | 2004-05-04 | 2004-05-04 | Tuesday | individuals
Rough-in sewer & water | 16 | 2004-05-04 | 2004-05-04 | 2004-05-04 | Tuesday | contracted
Set floor joists | 15 | 2004-05-05 | 2004-05-05 | 2004-05-05 | Wednesday | individuals
Rough-in plumbing | 17 | 2004-05-05 | 2004-05-05 | 2004-05-05 | Wednesday | contracted
Cap basement | 18 | 2004-05-06 | 2004-05-06 | 2004-05-06 | Thursday | individuals
Rough plumbing inspection |  |  |  | 2004-05-06 | Thursday | Construction Manager
Deliver wall panels | 19 | 2004-05-07 | 2004-05-07 | 2004-05-07 | Friday | individuals
Put up wall panels, set trusses | 20 | 2004-05-08 | 2004-05-08 | 2004-05-08 | Saturday | individuals
Sheath & tar paper roof | 25 | 2004-05-15 | 2004-05-15 | 2004-05-15 | Saturday | Carleton College - 7
Shingle roof | 28 | 2004-05-18 | 2004-05-18 | 2004-05-18 | Tuesday | Goodhue High School Honor Society - 15
Shingle roof, frame porch |  | 2004-06-12 | 2004-05-25 | 2004-06-12 | Saturday | St. Joseph's Catholic Church
Frame interior walls, install foundation drain system |  | 2004-06-19 |  | 2004-06-19 | Saturday | United Lutheran, Red Wing
level & prepare basement floor |  | 2004-06-12 |  | 2004-06-19 | Saturday | individuals
install foundation drain system | 31 | 2004-06-22 | 2004-05-29 | 2004-06-22 | Tuesday | Wells Fargo - 3
Pour basement floor | 24 | 2004-06-24 | 2004-05-13 | 2004-06-24 | Thursday | Red Wing Professional Firefighters
Pour basement floor, frame interior walls, install foundation drain system; move in shower/tub units | 24 | 2004-06-24 | 2004-05-13 | 2004-06-24 | Thursday | Christ Lutheran, De Forest, WI
Backfill basement walls | 21 | 2004-06-25 | 2004-05-10 | 2004-06-25 | Friday | contracted
Grade lot & remove debris | 22 | 2004-06-28 | 2004-05-10 | 2004-06-25 | Friday | contracted
Frame interior walls, sheath gable ends, dig out window well | 29 | 2004-06-26 |  | 2004-06-26 | Saturday | Christ Lutheran, De Forest, WI
work on porch & shingling | 30 | 2004-06-29 |  | 2004-06-29 | Tuesday
install windows, interior framing |  | 2004-07-03 |  | 2004-07-03 | Saturday
install windows, interior framing |  | 2004-07-06 |  | 2004-07-06 | Tuesday | Wells Fargo - 9
install rough pluming & upper level shower/tub unit |  | 2004-07-01 |  | 2004-07-08 | Thursday | contracted
install electric |  | 2004-06-30 |  | 2004-07-09 | Friday | contracted
connect power & gas |  | 2004-07-09 |  | 2004-07-09 | Friday | Xcel
install windows, interior framing |  | 2004-07-10 |  | 2004-07-10 | Saturday | Concordia Lutheran Church
install rough pluming & lower level shower/tub unit |  | 2004-07-09 |  | 2004-07-12 | Monday | contracted
install rough heat / electric |  | 2004-07-09 |  | 2004-07-12 | Monday | contracted
install rough pluming & lower level shower/tub unit |  | 2004-07-09 |  | 2004-07-13 | Tuesday | contracted
install rough heat / electric |  | 2004-07-09 |  | 2004-07-13 | Tuesday | contracted
shingle porch, dig out window wells; insulate walls |  | 2004-07-13 |  | 2004-07-13 | Tuesday | First United Methodist Church
Install water meter | 59 |  |  | 2004-07-13 | Tuesday | contracted
Install exterior faucets, dryer vents, water heater |  |  |  | 2004-07-15 | Thursday | contracted
install fascia & soffits; rap sheathing, install windows, insulate walls |  | 2004-07-17 |  | 2004-07-17 | Saturday | First English Lutheran Church, Cannon Falls
dig holes for porch & ramp footings & miscellaneous tasks |  | 2004-07-19 |  | 2004-07-19 | Monday | Individuals (food: United Lutheran: Joie Lee)
Tape sheathing rap; install windows; adjust window wells | 33 | 2004-07-20 |  | 2004-07-20 | Tuesday | First Christian Church - Baxter Springs, KS (food: United Redeemer: Ruth Reppe)
|  | 2004-07-20 |  | 2004-07-20 | Tuesday | Wells Fargo (canceled-no materials)
install heating ducts |  |  |  | 2004-07-22 | Thursday | contracted
siding; building stairway, install windows | 38 | 2004-07-22 |  | 2004-07-22 | Thursday | First Christian Church - Baxter Springs, KS (food: Eddlemon)
electrical |  |  |  | 2004-07-23 | Friday | contracted
install siding; install exterior door & locksets | 41 | 2004-07-23 |  | 2004-07-23 | Friday | First Christian Church - Baxter Springs, KS (food: Olsen & Santee)
install door & siding; dig trent for electrical service to garage |  | 2004-07-24 |  | 2004-07-24 | Saturday | First National Bank - Michelle - 8
insulate & poly walls; install siding; framing |  | 2004-07-27 |  | 2004-07-27 | Tuesday
interior framing |  | 2004-07-31 |  | 2004-07-31 | Saturday | St. Joseph's Catholic Church
interior framing |  | 2004-08-03 |  | 2004-08-03 | Tuesday | Wells Fargo
complete electrical work & inspection |  |  |  | 2004-08-04 | Wednesday | contracted
insulate walls; install siding |  | 2004-08-07 |  | 2004-08-07 | Saturday | First Lutheran (Red Wing) - no show
Request framing inspection |  |  |  | 2004-08-09 | Monday | Construction Manager
porch, basement window |  | 2004-08-10 |  | 2004-08-10 | Tuesday | Wells Fargo & Red Wing Shoe (Chrisy)
insulate & poly walls |  |  |  | 2004-08-11 | Wednesday
insulate & poly walls |  |  |  | 2004-08-12 | Thursday
Request insulation inspection |  | 2004-08-13 |  | 2004-08-13 | Friday | Construction Manager
insulate & poly walls |  |  |  | 2004-08-14 | Saturday | First Lutheran (Red Wing)
insulate & poly walls |  |  |  | 2004-08-17 | Tuesday | Fairview Red Wing Clinic
hang drywall |  | 2004-08-18 |  | 2004-08-18 | Wednesday | Treasure Island Maintenance crew
hang drywall |  |  |  | 2004-08-19 | Thursday
hang drywall |  |  |  | 2004-08-20 | Friday
hang drywall |  |  |  | 2004-08-21 | Saturday | First United Methodist Church
tape drywall |  |  |  | 2004-08-23 | Monday | contracted & volunteers
tape drywall |  |  |  | 2004-08-24 | Tuesday | contracted & volunteers
tape drywall |  |  |  | 2004-08-25 | Wednesday | contracted & volunteers
tape drywall; prime walls & ceilings |  |  |  | 2004-08-26 | Thursday | contracted & volunteers
tape drywall; prime walls & ceilings; order kitchen & bath cabinets |  |  |  | 2004-08-27 | Friday | contracted & volunteers
Spray walls & ceilings |  |  |  | 2004-08-28 | Saturday | contracted
tape drywall; prime walls & ceilings |  |  |  | 2004-08-30 | Monday | contracted & volunteers
tape drywall; prime walls & ceilings |  |  |  | 2004-08-31 | Tuesday | contracted & volunteers
Spray walls & ceilings |  |  |  | 2004-09-01 | Wednesday | contracted
Insulate ceiling |  | 2004-08-23 |  | 2004-09-01 | Wednesday | contracted
tape drywall; prime walls & ceilings |  |  |  | 2004-09-02 | Thursday | contracted & volunteers
tape drywall; prime walls & ceilings |  | 2004-08-12 |  | 2004-09-03 | Friday | contracted & volunteers
tape drywall; prime walls & ceilings; extend window wells |  | 2004-09-04 |  | 2004-09-04 | Saturday | contracted & volunteers
connect circuit to garage |  |  |  | 2004-09-07 | Tuesday | contracted
Stain & poly interior doors & trim |  | 2004-09-07 |  | 2004-09-07 | Tuesday
Install underlayment & vinyl in kitchen |  |  |  | 2004-09-08 | Wednesday | contracted
Stain & poly interior doors & trim |  | 2004-09-08 |  | 2004-09-08 | Wednesday
work on ramp |  | 2004-09-09 |  | 2004-09-09 | Thursday
complete extensions to window wells; mud drywall |  | 2004-09-11 |  | 2004-09-11 | Saturday
Install kitchen cabinets |  | 2004-09-22 |  | 2004-09-14 | Tuesday
complete spraying & painting walls |  |  |  | 2004-09-16 | Thursday | contracted (Bushinger resigns)
Install electric fixtures | 54 | 2004-10-01 |  | 2004-09-17 | Friday | contracted
varnish trim & interior doors |  | 2004-09-18 |  | 2004-09-18 | Saturday
install ceramic tile in upper bath |  | 2004-09-17 |  | 2004-09-20 | Monday | contracted
spread black dirt fill around perimeter |  | 2004-09-20 |  | 2004-09-24 | Friday | contracted
Complete heating installation |  |  |  | 2004-09-24 | Friday | contracted
varnish & stain trim & interior doors; cut out & remove molding drywall from basement; build ramp; clean basement |  |  |  | 2004-09-25 | Saturday | Board members
complete electrical work & inspection |  |  |  | 2004-09-29 | Wednesday | contracted
varnish trim & interior doors |  | 1 |  |  | Sunday
replace molding drywall in basement, finish, & paint |  | 2
Install trim & interior doors |  | 3 |  |  | Tuesday
complete front porch; complete siding, soffit, & fascia |  | 4 |  |  | Wednesday
Install vinyl flooring in LL bath |  | 5 |  |  | Thursday | contracted
Install kitchen/bath cabinets |  | 6 |  |  | Friday
Install kitchen countertops | 47 | 7 |  |  | Saturday
Pour sidewalk |  | 8 |  |  | Sunday
landscape; seed/sod lot | 51 | 9 |  |  | Monday | Cross of Christ Lutheran Youth (task not date)
Install window shades | 52 | 10 |  |  | Tuesday
Install gutters & downspouts | 62 | 11 |  |  | Wednesday | contracted
Install water closets | 65 | 12 |  |  | Thursday | contracted
Install bathroom lavatories | 66 | 13 |  |  | Friday | contracted
Install kitchen sink, Connect gas | 67 | 14 |  |  | Saturday | contracted
Lay carpet | 69 | 15 |  |  | Sunday | contracted
Request plumbing & heating inspection | 70 | 16 |  |  | Monday | Construction Manager
clean out garage |  | 17 |  |  | Tuesday
Request final inspection | 71 | 18 |  |  | Wednesday | Construction Manager
Walkthrough--HFH & family | 72 | 19 |  |  | Thursday
Celebration/ house dedication | 73 | 20 |  |  | Friday | Family, Friends, Supporters, Churches, Donors, Volunteers, Board & Committee Members
Formulas:
Scheduled Date = [reference date]