2. ORGANIZATION OF THE VIL1AGE

2.1. Structure

2.1.1. International Level

A. Role of International Office

Nations planning to host Villages inform the International Office of their intention, one year in advance. The International Office determines which nations should be invited to each Village, bearing in mind the total number of delegations each nation wishes to send and allocating places directly related to the number of Villages each National Association itself hosts. Delegation placements are also based on achieving a balance of cultures and languages in each Village. At least one place in each Village is reserved for a delegation from a new nation to the CISV programme. This schedule of Villages and delegations has come to be known as the “Football Pool” in CISV slang/terminology.

Invitations are sent from the International Office to National Associations inviting them to send delegations to particular Villages. National Associations will distribute these invitations among their Chapters. (See Appendix 10.6.0.1)

A sample of the football pool is included in the Appendix (please see Appendix 10.1).On the left side of the page are listed vertically the member nations and on top, listed horizontally, are the Villages scheduled for the year. The marks under a vertical column indicate the countries invited to a Village. When read horizontally, the marks indicate the invitations allocated for each nation. The symbols indicate the sex of the Adult Delegate:

 female;  male;  either.

B. Role of International Village Committee

The IVC-s role is to monitor Villages, provide recommendation for changes in program and procedure to the International Board, and to assist Chapters or National Associations that are beginning or maintaining a Village programme consistent with CISV rules, standards or recommendations. The Committee cooperates with Interchange, Seminar, Local Work, Promotion, Research, and other international committees on projects/concerns of common interest.

C. Village Calendar

Villages last four weeks (28 days) and are held in a variety of locations around the world. While the specific dates of the Village are decided by the host nation, most Villages in the Northern Hemisphere are held between the beginning of July and the middle of August. Villages in the Southern Hemisphere are sometimes held during December/ January.

2.1.1 CALENDAR

| Stages | Hosting Villages |  | Outgoing Delegations |
| --- | --- | --- | --- |
| 1 | National Report forms are due to International Office (I.O.) with commitments for the following year’s Village and the request for the number of delegations and JC’s to be sent out. | J U N E |  |
| 2 | At the IBM the preliminary schedule of Villages and delegations (Football Pool) is discussed | A U G U S T |  |
| National Board Meeting to be held 3 4 | National Association/Local Chapter should decide on the Village site and start raising funds I.O. sends out the final Football Pool to all national Associations Village information Form to be returned to I.O. (form supplied by I.O.). This should include as much information as is available at this time but the form should not be held back if any details are missing. The form should be sent in on time. The missing information should be sent as soon as is available. (Refer to 10.2) Host staff to be chosen and director appointed. Director should attend all local board meetings/local village committee meetings. Regular meetings of host staff to continue. | S E P T E M B E R O C T O B E R |  |
| 5 | Fund raising activities should be in progress. | N O V E M B E R | I.O. sends out official invitations for delegations and Junior Counsellors. These invitations should be accepted or otherwise dealt with by the end of the following month. If a nation is unable to accept an invitation, the host country and I.O. must be informed. It is not enough to just inform I.O. - it is not their responsibility to let the host country know. |
| 6 |  | D E C E M B E R | Acceptance of Village invitations due at I.O. As the host nation receives notification of acceptance to their Village from I.O., they should write to the contact person named giving as much information as possible using suggested letter form. |

| Stages | Hosting Villages |  | Outgoing Delegations |
| --- | --- | --- | --- |
| 7 | Last opportunity to inform I.O. of any change of dates for Village travel plans. | J A N U A R Y | Selection of adult delegates, JC and children should be in progress and Leadership Training started. |
| 8 | Host staff must send pre-Village Information No. 1 (Refer to Chapter 6) | F E B R U A R Y | Adult Delegates should write to Village director. |
| 9 |  | M A R C H | selection of adult, Jcs, and children should be completed by now. Adult Delegates and Jcs must be in direct contact with host Village Director. Adult Delegates start meetings with child delegates. Health and Legal forms are distributed to Adult delegate and to families of children Pay delegation fees |
| 10 | Second pre-Village information should be sent to visiting delegations. local fund raising continues. Support should also be sought in other ways e.g. by asking for services and materials | A P R I L |  |
| 11 |  | M A Y | Delegation information sheet and delegation travel sheet should be sent to Village Director. |
| 12 | Village Directors send directory to I.O. Evaluation concerns to I.O. and I.V.C. as indicated (see 10.7.3) | J U N E A U G U S T | Final meeting of outgoing delegation, parents and adult Delegates with the local committee to collect health and legal forms. Complete insurance coverage for all delegates to be checked by National Association/local Chapters. |

* National Association/Local Chapter having Villages in December/January adjust calendar accordingly.

2.1.2. National and Local Level

The National Associations carry out the following functions in connection with the Village:

-	Dealing with invitations to CISV camps held both inside and outside their countries, and involving  nationals of their respective nations.

-	Handling of CISV correspondence relating to Village matters.

-	Dealing with international Village fees

-	Organizing and funding Villages within the nation.

2.2. Funding

2.2.1. International

The bulk of the funding for the work of the International Association, including the I.O. (International Office), comes from dues contributed by the National Associations and from Participation Fees paid by participants of all international activities in the programme.

2.2.2. National and Local

The major portion of all CISV fund raising is done at national and local levels. Funds to send delegations and Junior Counsellors to CISV Villages must ordinarily be raised within the nation sending the delegation and JCs. Raising money to hold a CISV Village is the responsibility of the host country, either nationally or on the part of a Local Chapter. Methods of raising money and defining CISV membership must, of necessity, vary greatly from country to country and no general formula can be laid down.

2.2.3. Village Participation Fees.

Each participant of a CISV programme must pay a participation fee to the I.O. Details of current international fees are included in the INFO FILE and the minutes of the most current International Board Meeting.