「小眼睛看大世界　小腳板走天漄」

Easter Service Project

4th Committee Meeting

Date: 6 Mar 2005

Time: 1300-1500

Venue: KFC of Hollywood Plaza

Chairperson: Estella Tsang

Present: Estella Tsang, Christy Lau, Kristy Chan, Annie Chan,

Eunice Chau,

Absent: Cherry Wong, Maggie Chan,

Minutes

The meeting was opened at 13:05 hours after the unanimous adoption of the agenda.

- Adopt the agenda if thought fit

- To approve the minutes of the previous meeting

- To discuss the working schedule

- Spare Preparation Days: 24,25/03

- Working Schedule of Easter Service

Service Dates:

26/3, 28/3  11:45am Committee meets at Lam Tin MTR station Hang Seng Bank

12:30pm Duty Cadets meet at Lam Tin MTR station Hang Seng Bank

5:00pm. Service End

30/3  To be confirmed

* Each division needs to recruit 8 duty cadets on each service dates (except 30/3-to be confirm)

~The actual time of the following is needed to be confirmed later~

13/3(Sun) Preparation Works

Work prepared before 13/3 / Person / Work to be done on 13/3

- Ticket Finish making /Christy /Write down the name

-(澳洲劇場)  Finish劇本 /Maggie & Cherry / Prove

-(齊來拼一拼)  Drawing /Kristy/ Color & 貼紙皮

- (旗仔跳舞)  Buy and cut the materials/ Estella / Make the flag

- (日本錢幣知多少) Prepare the papers of money/ Tracy /貼紙皮

- (韓式收賣佬) Finish making papers (each x3)/ Eunice /貼紙皮

- (向左走、向右走) Finish making papers and questions/ Annie /貼紙皮

- (以話傳話) Find the sentences of “大家好,你今日開不開心呀? 多謝”/All/Prove

- Pre-do the 小手工 : 幸運符&皇冠

- Do the envelops with papers inside (Name of different countries)

- MC sheets If prepare

- Discuss the things about outing venue

Things needed to be brought by every committee

- 大量紙皮 – Cutter – Scissors – Color pencil – some A4 papers

- Black marker – Materials of the games – Basic stationeries

Thing needed to be brought by Christy

- 毛公仔x6

Things bought by Kristy

- 封箱膠紙x3 – glue stickx1 – 雙面膠紙x1 -皇冠條

18/3(Fri) Committee & duty cadets’ meeting with the centre

20/3(Sun) Preparation Works

- Finish all the remaining preparation

- 排Drama

- Pre-games

Things needed to be brought by every committee

-  大量碎紙(need to collect before the preparation)

- Music by Tracy

- Confirmed lists of food and money Eunice & Maggie

- Materials of the games

Duties on that service days

- Take photos by Estella & Kristy

- MC 26/3 by Annie & Christy

28/3 by Eunice & Tracy

- Responsible for buying food & Souvenirs before by Eunice & Maggie

(Inform Estella by phone on 16/3 about the draft lists and required of the food and souvenirs)

- To discuss the detail of the proposal:

  - Programmes

    - Games

- 2 more spare games are needed

- Game: Chinese dance has been cancelled due to the weak ability of clients

    - Outing Venue and refreshment

- Venue: HK Science Museum

- 復康巴士 1000-1400    ( to be confirmed later)

- Taking Breakfast with clients before the outing  ( sponsor is needed)

*Possible problems encounted:

- Time for outing is too long

- HK Science Museum might bored the clients

- No lunch time could be offered due to the limited time

- Booking of 復康巴士   (Tel: 2817 8154)

  - Financial Budget

- $1500 is approved

- A.O.B.

- Next Meeting

- To be confirmed later

- Adjournment

There being no other business, the meeting was adjournment at 15:15.

Prepared by,                       				 Approved by,

Cherry Wong                      					Candy Lee Hoi Ping

Secretary                    					        Person in Charge