## Table1
TR |  |  | MET | FC1 | FC2 | Event | Notes | EDT
5 | -- | 0 | 0:55 |  | Flight | CTS | Call each console to verify that they are ready to take their position | 9:35
5 | -- | 0 | 0:54 |  | Flight | Time Sync | Advise MCC to confirm sync of computer clocks. Then orally countdown with Flight clock. CTS to check for synchronization. | 9:36
5 | -- | 0 | 0:53 | FIDO | Flight | INITIATE: MCC Abort Advisory Check | PRESS Abort Switch and then release. CONFIRM. | 9:37
5 | -- | 0 | 0:52 | Capcom | Flight | ADVISE Crew: Initiate Orbiter Abort Advisory Check | CDR: Activate Abort Switch and then deactivate. CONFIRM. | 9:38
C | -- | 0 | 0:50 | ### | Booster | SRB Jnt Htr Shutdown | PRESS SRB Jnt Htr A & B | 9:40
5 | -- | 0 | 0:47 | Flight | FAO | FAO Update | During an FAO Update advise Flight about whether the mission is proceeding on schedule. Make any suggested changes to the Flight Plan | 9:43
C | -- | 0 | 0:45 | Flight | FIDO | ADVISE Crew: Initiate IMU Preflight Alignment | CDR: Activate IMU Alignment A, B, C FIDO: After IDL greenlines, check MacMECO to CONFIRM stabilized for launch at 28.60 N lat, 80.60 W long, 00 NM altitude | 9:45
*** | -- | 0 | 0:45 |  | Surgeon | Preflight Vitals | Confirm nominal as each set of vitals is sent from Closeout Crew. | 9:45
5 | -- | 0 | 0:44 | FIDO | Flight | STATUS: MECO Targets | FIDO: Check MacMECO and confirm that MECO targets are set at ~Vi: 25915 fps ~Height 57 nm
C | -- | 0 | 0:43 | Flight | MAX | ADVISE Crew: Initiate Boiler activation | PLT: Blr Cntlr 1,2,3 ON Blr N2 Sply 1,2,3 ON MAX: CONFIRM Activation of above. Monitor Blr Temps on tele scrn. | 9:47
5 | -- | 0 | 0:42 | GNC | Flight | STATUS: TDRS system | TDRS status? WSC status? TDRZ (for OMS insertion)? | 9:48
5 | -- | 0 | 0:41 | Flight | Booster | ADVISE Crew: Initiate Aft RCS Program Sequence | MS2: Input GNC 23 RCS into SPOC and GNC SYS SUMM 2. CONFIRM with MCC. Booster: Check for IDL greenlines on all of the following: ~L Aft RCS Oxid He Pres Iso Vlv A ~L Aft RCS Oxid He Pres Iso Vlv B ~L Aft RCS Oxid He Pres Dual He Rgltr A ~L Aft RCS Oxid He Pres Dual Rgltr AA ~L Aft RCS Oxid He Pres Dual Rgltr B ~L Aft RCS Oxid He Pres Dual He Rgltr BB ~L Aft RCS Oxid Quad Ck Vlv A ~L Aft RCS Oxid Quad Ck Vlv B ~L Aft RCS Oxid Quad Ck Vlv C ~L Aft RCS Oxid Quad Ck Vlv D | 9:49
5 | -- | 0 | 0:41 | " | " | " | ~L Aft RCS Oxid He Pres Relief Vlv ~L Aft RCS Oxid Tk 1/2 Iso Vlv ~L Aft RCS Oxid Tk 3/4/5 Iso Vlv A ~L Aft RCS Oxid Tk 3/4/5 Iso Vlv B ~L Aft RCS Oxid XFeed 1/2 Vlv ~L Aft RCS Oxid XFeed 3/4/5 Vlv ~L Aft RCS Oxid Manf Iso Vlv 1 ~L Aft RCS Oxid Manf Iso Vlv 2 ~L Aft RCS Oxid Manf Iso Vlv 3 ~L Aft RCS Oxid Manf Iso Vlv 4 ~L Aft RCS Oxid Manf Iso Vlv 5 ADVISE Crew: L Aft RCS Oxidizer Sequence is nominal | 9:49
5 | -- | 0 | 0:41 | " | " | " | Booster: Check for IDL greenlines on all of the following: ~L Aft RCS Fuel He Pres Iso Vlv A ~L Aft RCS Fuel He Pres Iso Vlv B ~L Aft RCS Fuel He Pres Dual He Rgltr A ~L Aft RCS Fuel He Pres Dual Rgltr AA ~L Aft RCS Fuel He Pres Dual Rgltr B ~L Aft RCS Fuel He Pres Dual He Rgltr BB ~L Aft RCS Fuel Quad Ck Vlv A ~L Aft RCS Fuel Quad Ck Vlv B ~L Aft RCS Fuel Quad Ck Vlv C ~L Aft RCS Fuel Quad Ck Vlv D | 9:49
5 | -- | 0 | 0:41 | " | " | " | ~L Aft RCS Fuel He Pres Relief Vlv ~L Aft RCS Fuel Tk 1/2 Iso Vlv ~L Aft RCS Fuel Tk 3/4/5 Iso Vlv A ~L Aft RCS Fuel Tk 3/4/5 Iso Vlv B ~L Aft RCS Fuel XFeed 1/2 Vlv ~L Aft RCS Fuel XFeed 3/4/5 Vlv ~L Aft RCS Fuel Manf Iso Vlv 1 ~L Aft RCS Fuel Manf Iso Vlv 2 ~L Aft RCS Fuel Manf Iso Vlv 3 ~L Aft RCS Fuel Manf Iso Vlv 4 ~L Aft RCS Fuel Manf Iso Vlv 5 ADVISE Crew: L Aft RCS Fuel Sequence is nominal | 9:49
5 | -- | 0 | 0:41 | " | " | " | Booster: Check for IDL greenlines on all of the following: ~R Aft RCS Fuel He Pres Iso Vlv A ~R Aft RCS Fuel He Pres Iso Vlv B ~R Aft RCS Fuel He Pres Dual He Rgltr A ~R Aft RCS Fuel He Pres Dual Rgltr AA ~R Aft RCS Fuel He Pres Dual Rgltr B ~R Aft RCS Fuel He Pres Dual He Rgltr BB ~R Aft RCS Fuel Quad Ck Vlv A ~R Aft RCS Fuel Quad Ck Vlv B ~R Aft RCS Fuel Quad Ck Vlv C ~R Aft RCS Fuel Quad Ck Vlv D | 9:49
5 | -- | 0 | 0:41 | " | " | " | ~R Aft RCS Fuel He Pres Relief Vlv ~R Aft RCS Fuel Tk 1/2 Iso Vlv ~R Aft RCS Fuel Tk 3/4/5 Iso Vlv A ~R Aft RCS Fuel Tk 3/4/5 Iso Vlv B ~R Aft RCS Fuel XFeed 1/2 Vlv ~R Aft RCS Fuel XFeed 3/4/5 Vlv ~R Aft RCS Fuel Manf Iso Vlv 1 ~R Aft RCS Fuel Manf Iso Vlv 2 ~R Aft RCS Fuel Manf Iso Vlv 3 ~R Aft RCS Fuel Manf Iso Vlv 4 ~R Aft RCS Fuel Manf Iso Vlv 5 ADVISE Crew: R Aft RCS Fuel Sequence is nominal and Aft RCS Program Sequence is complete | 9:49
5 | -- | 0 | 0:41 | " | " | " | Booster: Check for IDL greenlines on all of the following: ~R Aft RCS Oxid He Pres Iso Vlv A ~R Aft RCS Oxid He Pres Iso Vlv B ~R Aft RCS Oxid He Pres Dual He Rgltr A ~R Aft RCS Oxid He Pres Dual Rgltr AA ~R Aft RCS Oxid He Pres Dual Rgltr B ~R Aft RCS Oxid He Pres Dual He Rgltr BB ~R Aft RCS Oxid Quad Ck Vlv A ~R Aft RCS Oxid Quad Ck Vlv B ~R Aft RCS Oxid Quad Ck Vlv C ~R Aft RCS Oxid Quad Ck Vlv D | 9:49
5 | -- | 0 | 0:41 | " | " | " | ~R Aft RCS Oxid He Pres Relief Vlv ~R Aft RCS Oxid Tk 1/2 Iso Vlv ~R Aft RCS Oxid Tk 3/4/5 Iso Vlv A ~R Aft RCS Oxid Tk 3/4/5 Iso Vlv B ~R Aft RCS Oxid XFeed 1/2 Vlv ~R Aft RCS Oxid XFeed 3/4/5 Vlv ~R Aft RCS Oxid Manf Iso Vlv 1 ~R Aft RCS Oxid Manf Iso Vlv 2 ~R Aft RCS Oxid Manf Iso Vlv 3 ~R Aft RCS Oxid Manf Iso Vlv 4 ~R Aft RCS Oxid Manf Iso Vlv 5 ADVISE Crew: R Aft RCS Oxidizer Sequence is nominal | 9:49
5 | -- | 0 | 0:40 | Flight | Booster | ADVISE Crew: Initiate Fwd RCS Program Sequence | MS2: Input GNC 23F RCS into SPOC and GNC SYS SUMM 2F CONFIRM with MCC. Booster: Check for IDL greenlines on all of the following: ~Fwd RCS Oxid He Pres Iso Vlv A ~Fwd RCS Oxid He Pres Iso Vlv B ~Fwd RCS Oxid He Pres Dual He Rgltr A ~Fwd RCS Oxid He Pres Dual Rgltr AA ~Fwd RCS Oxid He Pres Dual Rgltr B ~Fwd RCS Oxid He Pres Dual He Rgltr BB ~Fwd RCS Oxid Quad Ck Vlv A ~Fwd RCS Oxid Quad Ck Vlv B ~Fwd RCS Oxid Quad Ck Vlv C ~Fwd RCS Oxid Quad Ck Vlv D | 9:50
5 | -- | 0 | 0:40 | " | " | " | ~Fwd RCS Oxid He Pres Relief Vlv ~Fwd RCS Oxid Tk 1/2 Iso Vlv ~Fwd RCS Oxid Tk 3/4/5 Iso Vlv A ~Fwd RCS Oxid Tk 3/4/5 Iso Vlv B ~Fwd RCS Oxid XFeed 1/2 Vlv ~Fwd RCS Oxid XFeed 3/4/5 Vlv ~Fwd RCS Oxid Manf Iso Vlv 1 ~Fwd RCS Oxid Manf Iso Vlv 2 ~Fwd RCS Oxid Manf Iso Vlv 3 ~Fwd RCS Oxid Manf Iso Vlv 4 ~Fwd RCS Oxid Manf Iso Vlv 5 ADVISE Crew: Fwd RCS Oxidizer Sequence is nominal | 9:50
5 | -- | 0 | 0:40 | " | " | " | Booster: Check for IDL greenlines on all of the following: ~Fwd RCS Fuel He Pres Iso Vlv A ~Fwd RCS Fuel He Pres Iso Vlv B ~Fwd RCS Fuel He Pres Dual He Rgltr A ~Fwd RCS Fuel He Pres Dual Rgltr AA ~Fwd RCS Fuel He Pres Dual Rgltr B ~Fwd RCS Fuel He Pres Dual He Rgltr BB ~Fwd RCS Fuel Quad Ck Vlv A ~Fwd RCS Fuel Quad Ck Vlv B ~Fwd RCS Fuel Quad Ck Vlv C ~Fwd RCS Fuel Quad Ck Vlv D | 9:50
5 | -- | 0 | 0:40 | " | " | " | ~Fwd RCS Fuel He Pres Relief Vlv ~Fwd RCS Fuel Tk 1/2 Iso Vlv ~Fwd RCS Fuel Tk 3/4/5 Iso Vlv A ~Fwd RCS Fuel Tk 3/4/5 Iso Vlv B ~Fwd RCS Fuel XFeed 1/2 Vlv ~Fwd RCS Fuel XFeed 3/4/5 Vlv ~Fwd RCS Fuel Manf Iso Vlv 1 ~Fwd RCS Fuel Manf Iso Vlv 2 ~Fwd RCS Fuel Manf Iso Vlv 3 ~Fwd RCS Fuel Manf Iso Vlv 4 ~Fwd RCS Fuel Manf Iso Vlv 5 ADVISE Crew: Fwd RCS Fuel Sequence is nominal and Fwd RCS Program Sequence Complete | 9:50
C | -- | 0 | 0:36 | Booster | Flight | Activate SRB Chamber Pres Check | Activate and monitor SRB pres on display. This event is complete when pres >2000 psi. CONFIRM and deactivate. | 9:54
5 | -- | 0 | 0:35 | Flight | Booster | Advise Crew: RCS Tanks Pressure and Quantity Status | Check all of the RCS Fuel, Oxid, and He tank pressures and quantities. | 9:55
5 | -- | 0 | 0:35 | GNC | Flight | STATUS: KSC and Primary TAL Site (Ben Guerir, Morocco) | GNC: Assume nominal conditions unless SMG has notified you otherwise | 9:55
5 | -- | 0 | 0:35 | No Call | Lead MET | SMG Launch Mtg | Lead MET and all available Flight Directors (off-duty) meet to go over any weather conditions that could interfere with launch. Flight Directors contact Red Team Flight if necessary. | 9:55
C | -- | 0 | 0:34 | Flight | EECOM | ADVISE Crew: Cabin Leak Check | PLT: Cbn Vnt A & B CLOSE. Complete when Cabin Pres = 16.7 psi for 1 minute. CONFIRM. (Alarm should sound when psi > 14.7) | 9:56
C | -- | 0 | 0:32 | Flight | MAX | ADVISE Crew: Initiate Primary Avionics and BFS (Backup Flt Sys) transfer | MS2: SPOC input Mode 5 | 9:58
5 | -- | 0 | 0:32 | GNC | Flight | STATUS: Preliminary meteorological launch status | Contact SMG for update on weather conditions for launch | 9:58
1 | -- | 0 | 0:31 | Flight | EECOM | ADVISE Crew: Activate PPO2 Sensor | PLT: PPO2 Sensor ON | 9:59
1 | -- | 0 | 0:30 | Flight | EECOM | ADVISE Crew: Set Atmospheric Pres control to auto | PLT: Atm Pres AUTO | 10:00
C | -- | 0 | 0:30 | ### | MAX | GLS Mainline Activated | PRESS GLS Mainline | 10:00
C | -- | 0 | 0:29 | ### | MAX | GLS presequence activated | PRESS GLS Preseq | 10:01
C | -- | 0 | 0:29 | Flight | EECOM | ADVISE Crew: Perform cabin vent test | PLT: Cbn Vnt A & B OPEN. Complete when Cabin Pres = approx 14.7 psi. CONFIRM. | 10:01
5 | -- | 0 | 0:28 | Flight | FAO | FAO Update |  | 10:02
1 | -- | 0 | 0:27 | Flight | EECOM | NOTIFY Crew: FC 1 Status | EECOM: Check for IDL Greenlines on following: ~FC1 O2 Reac Vlv ~FC1 H2 Reac Vlv ~PRSD O2 Tk1 Rgltr Vlv ~PRSD O2 Tk1 Iso Vlv ~PRSD H2 Tk1 Rgltr Vlv ~PRSD H2 Tk1 Iso Vlv CONFIRM: FC1 Status is nominal (after checking everything above) | 10:03
1 | -- | 0 | 0:27 | Flight | EECOM | NOTIFY Crew: FC 2 Status | EECOM: Check for IDL Greenlines on following: ~FC2 O2 Reac Vlv ~FC2 H2 Reac Vlv ~PRSD O2 Tk6 Rgltr Vlv ~PRSD O2 Tk6 Iso Vlv ~PRSD H2 Tk6 Rgltr Vlv ~PRSD H2 Tk6 Iso Vlv ~PRSD O2 Tk3 Rgltr Vlv ~PRSD O2 Tk3 Iso Vlv ~PRSD H2 Tk3 Rgltr Vlv ~PRSD H2 Tk3 Iso Vlv CONFIRM: FC2 Status is nominal (after checking everything above) | 10:03
1 | -- | 0 | 0:27 | Flight | EECOM | NOTIFY Crew: FC 3 Status | EECOM: Check for IDL Greenlines on following: ~FC3 O2 Reac Vlv ~FC3 H2 Reac Vlv CONFIRM: FC3 Status is nominal (after checking everything above) | 10:03
C | -- | 0 | 0:27 | Flight | EECOM | ADVISE Crew: Initate Fuel Cell Start Sequence | PLT: Activate the following: ~FC 1,2,3 Ctrlr ~FC1,2,3 Strt EECOM: Confirm IDL greenlines | 10:03
C | -- | 0 | 0:27 | Flight | EECOM | ADVISE Crew: Activate Avionics Bay Fans | PLT: Activate Avncs By Fn 1,2,3 EECOM: Confirm IDL greenlines | 10:03
5 | -- | 0 | 0:27 | Flight | EECOM | ADVISE Crew: PRSDTanks Pressure, Temp, and Quantity Status | Check all of the PRSD Tnk Pressures, Temps, and Qty | 10:03
5 | -- | 0 | 0:25 | Flight | GNC | ADVISE Crew: Met conditions for RTLS and TAL sites | GNC: Notify of any conditions that are off nominal. | 10:05
1 | -- | 0 | 0:25 | Flight | EECOM | ADVISE Crew: Close cabin vent valves | PLT: Cbn Vnt A & B CLOSE. Be sure that Cabin Vent test is complete first. | 10:05
3 | -- | 0 | 0:25 | Flight | EECOM | ADVISE Crew: Electrical Power Distribution System Status | Check the following voltage levels. All should be outputting 27-34 V. ~Mn Bus A ~Mn Bus B ~Mn Bus C ~Ess Bus A ~Ess Bus B ~Ess Bus C Check the following for IDL greenlines: ~Fwd Ld Ctrlr Assembly ~Fwd Pwr Ctrlr Assembly ~Aft Ld Ctrlr Assembly ~Aft Ld Ctrlr Assembly | 10:05
C | -- | 0 | 0:23 | Flight | FIDO | ADVISE Crew: Acitvate IMU Start | CDR: PRESS IMU Strt A,B,C FIDO: Confirm IDL greenlines | 10:07
2 | -- | 0 | 0:22 | Flight | EECOM | NOTIFY Crew: ECLSS Status | Check Pressures, Temps, Qty/IDL greenlines on following: ~Cbn Pres ~Cbn O2 Pct ~Cbn N2 Pct ~Cbn CO2 Pct ~GN2 Tk1 Sys1 Pres ~GN2 Tk 1 Sys 1 Qty ~GN2 Tk 1 Sys 1 Tmp ~GN2 Tk 2 Sys 1 Pres ~GN2 Tk 2 Sys 1 Qty ~GN2 Tk 2 Sys 1 Tmp ~GN2 Sys 1 Rgltr ~O2 Sys 1 Sply Vlv ~O2 Sys 1 Cbn Pres Rgltr ~GN2 Tk 1 Sys 2 Pres ~GN2 Tk 1 Sys 2 Qty ~GN2 Tk 1 Sys 2 Tmp ~GN2 Tk 2 Sys 2 Pres ~GN2 Tk 2 Sys 2 Qty ~GN2 Tk 2 Sys 2 Tmp ~GN2 Sys 2 Rgltr ~O2 Sys 2 Sply Vlv ~O2 Sys 2 Cbn Pres Rgltr
C | -- | 0 | 0:20 | Flight | MAX | ADVISE Crew: Activate GPC OPS 1 | MS2: SPOC input Mode 5 OPS 1 MAX: CONFIRM Mode 5 OPS 1 on tele scrn | 10:10
C | -- | 0 | 0:16 | Flight | Booster | ADVISE Crew: Initiate MPS Helium Pres | CDR: MPS He Iso A & B (for MPS 1,2,3) to OPEN Booster: CONFIRM when IDL greenlines | 10:14
C | -- | 0 | 0:16 | Flight | Booster | ADVISE Crew: Initiate Pneumatic Helium Pres | CDR: Pneu He Iso to OPEN Booster: CONFIRM when IDL greenlines | 10:14
*** | -- | 0 | 0:16 | Flight | Booster | ADVISE Crew: MPS Helium Pres Status | Check pressures, temps, and qty on MPS A & B (1,2,3). | 10:14
5 | -- | 0 | 0:15 | No Call | MAX | PBD Latch Status | Check PBD Latch 1-18 for IDL greenlines | 10:15
1 | -- | 0 | 0:14 | ### | MAX | SRB GN2 Purge Initiated | PRESS SRB GN2 Purge A & B | 10:16
*** | -- | 0 | 0:13 | Flight | Booster | STATUS: SRB HPU pres | Wait for SRB APU A & B to greenline on IDL before making the call | 10:17 | x
5 | -- | 0 | 0:13 | Capcom | Flight | ADVISE Crew: Initiate Final Orbiter Abort Advisory Check | CDR: Activate Abort Switch and then deactivate. CONFIRM. | 10:17
2 | -- | 0 | 0:12 | GNC | Flight | STATUS: Met Launch Status | GNC: Contact Lead MET for GO/NO GO for launch | 10:18
C | -- | 0 | 0:10 |  | Flight | POLL: Launch Readiness | GO/NO GO for launch. Controllers identify any constraints for launch. Capcom: GO/NO GO for launch from CDR | 10:20
C | -- | 0 | 0:09 | MAX | Flight | INITIATE: GLS Start | PRESS GLS Start | 10:21
C | -- | 0 | 0:09 | Flight | Booster | ADVISE Crew: Inititiate MPS Thrust Vector Control Activation Sequence | CDR: Activate the following: ~MPS Ctrlr 1,2,3 ~MPS EIU 1,2,3 ~MPS TVC Vlv 1,2,3 Booster: Confirm IDL greenlines | 10:21
1 | -- | 0 | 0:08 | Flight | EECOM | ADVISE Crew: Activate AC Sensors | PLT: AC Bus Snsr switches to ON | 10:22
1 | -- | 0 | 0:07 | MAX | Flight | OAA Retract | PRESS OAA NOTIFY Crew: OAA Retracted | 10:23
C | -- | 0 | 0:06 | Flight | MAX | ADVISE Crew: Initiate APU Prestart Sequence | PLT: CONFIRM the following switch positions: ~Blr N2 Sply 1,2,3 ON ~Blr Ctrlr ON | 10:24
C | -- | 0 | 0:06 | " | " | " | CDR: CONFIRM the following switch positions ~APU Fuel Tnk Vlv 1,2,3 CLOSE ~APU Fuel Pmp Vlv 1,2,3 CLOSE ~APU Ctrlr 1,2,3 OFF ~HPU Circ Pmp 1,2,3 ON ~APU Auto Shutdown ON NOTIFY MCC: APU Prestart Complete | 10:24
*** | -- | 0 | 0:06 | ### | MAX | CONFIRM: APU Prestart Status | MAX: Check all of the above for IDL greenlines | 10:24
C | -- | 0 | 0:05 | Flight | MAX | ADVISE Crew: Initiate APU Start | CDR: ~APU Fuel Tnk Vlv 1,2,3 OPEN ~APU Ctrlr 1,2,3 ON ~HPU Mn Pmp 1,2,3 ON ~HPU Circ Pmp 1,2,3 ON NOTIFY MCC: APU Start Complete | 10:25
*** | -- | 0 | 0:05 | ### | MAX | CONFIRM: APU Start Status | MAX: Check all of the above for IDL greenlines | 10:25
1 | -- | 0 | 0:05 | No Call | MAX | APU Secondary Status Check | Check the following pressures and temps: ~APU 1,2,3 Fuel Tk Pres ~APU 1,2,3 GN2 Tk Pres ~APU 1,2,3 Spd ~GGT 1,2,3 Temp ~GN2 Blr 1,2,3 Pres ~GN2 Inj Clnt 1,2,3 Pres Notify Flight immediately if anything is off-nominal | 10:25
2 | -- | 0 | 0:05 | ### | Booster | SRB and ET RSS Armed | PRESS SRB RSS Arm and ET RSS Arm | 10:25
C | -- | 0 | 0:05 | Flight | Booster | ADVISE Crew: Arm ET and SRBs | CDR: ET Arm ON SRB Arm ON Booster: CONFIRM IDL greenline | 10:25
5 | -- | 0 | 0:05 | No Call | MAX | Payload Bay Volatile Gas Check | MAX: Check PB Snsr for IDL greenline | 10:25
C | -- | 0 | 0:05 | ### | Booster | LOX F&D Vlv Closed | PRESS LOX F&D Vlv Monitor IDL for greenline Flight: Notify Crew | 10:25
C | -- | 0 | 0:05 | ### | Booster | LOX Drain Vlv Closed | PRESS LOX Drain Vlv Monitor IDL for greenline Flight: Notify Crew | 10:25
C | -- | 0 | 0:04 | ### | Booster | SSME Heaters shutdown | PRESS SSME Htr 1,2,3 | 10:26
C | -- | 0 | 0:04 | Flight | EECOM | NOTIFY Crew: Orbiter switch to internal power complete | EECOM: PRESS PRSD Transfer | 10:26
C | -- | 0 | 0:04 | Flight | MAX | NOTFY Crew: Initiate Orbiter Aerosurfaces check | MAX: PRESS Aerosurfaces Check | 10:26
1 | -- | 0 | 0:04 | No Call | Booster | SSME Vlv Htr Shutdown and SSME Purge | Booster: PRESS the following: ~SSME Vlv Htr Shtdn 1,2,3 ~SSME Purge | 10:26
C | -- | 0 | 0:04 | Flight | Booster | ADVISE Crew: Close SSME Valves | CDR: Deactivate SSME Vlv 1,2,3 Booster: Check for IDL greenlines | 10:26
C | -- | 0 | 0:03 | Flight | Booster | NOTIFY Crew: Main Engine gimbal check complete | Booster: PRESS SSME Lnch Pos 1,2,3 | 10:27
1 | -- | 0 | 0:03 | No Call | Booster | SRB GN2 Purge | Booster: PRESS SRB GN2 Purge | 10:27
C | -- | 0 | 0:03 | ### | Booster | ET LOX Pres Initiated | Booster: PRESS ET LOX Pres Monitor IDL for greenline Flight: Notify Crew | 10:27
C | -- | 0 | 0:03 | ### | MAX | GOX Vent Hood retraction (Beanie Cap) | PRESS GOX Vent Hood Retract Flight: Notify Crew | 10:27
C | -- | 0 | 0:02 | Flight | FAO | ADVISE Crew: Close and lock visors | CDR: Notify crew to close visors on helmets. | 10:28
C | -- | 0 | 0:02 | Capcom | Flight | Final Comm Check | CDR: Give status of AGL comm | 10:28
C | -- | 0 | 0:02 | ### | Booster | LH2 Fill Terminated | Booster: PRESS LH2 Fill Monitor IDL for greenline Flight: Notify Crew | 10:28
C | -- | 0 | 0:02 | ### | Booster | LH2 Topping Vlv and LH2 Vnt Vlv Closed | Booster: PRESS LH2 Topping Vlv and LH2 Vnt Vlv Notify Crew | 10:28
C | -- | 0 | 0:02 | ### | Booster | LH2 Pres Initiated | Booster: PRESS LH2 Pres Flight: Notify Crew | 10:28
C | -- | 0 | 0:01 | ### | Booster | LOX and LH2 F&D Vlvs Closed | Booster: PRESS LOX and LH2 F&D Vlvs Flight: Notify Crew | 10:29
C | -- | 0 | 0:01 | ''' | FAO | 60 seconds | Capcom: Relay same | 10:29
C | -- | 0 | 0:01 | No Call | MS1 | Status Check | Check for IDL Greenlines on APU, GPC, IMU, SSME, FC | 10:29
C | -- | 0 | 0:01 | ### | EECOM | Ground power removed | EECOM: PRESS Grnd Pwr Flight: Notify Crew | 10:29
C | -- | 0 | 0:01 | ### | MAX | Cut Off Armed | MAX: PRESS GLS Cut Off | 10:29
C | -- | 0 | 0:01 | No Call | MS2 | Input VENT DOOR CTRL OPEN | MAX: Check for IDL Greenlines on: ~L Vnt Purge Dr 1-9 ~R Vnt Purge Dr 1-9 | 10:29
C | -- | 0 | 0:01 | ### | Capcom | GLS AutoSequence Initiated | MAX: PRESS GLS AutoSeq Start | 10:29
C | -- | 0 | 0:00 | No Call | MS1 | Status Check | Check for IDL Greenlines on APU, GPC, IMU, SSME, FC Monitor constantly from this point until ET Sep | 10:30
C | -- | 0 | 0:00 | ### | Capcom | 30 seconds |  | 10:30
C | -- | 0 | 0:00 | ### | Booster | SRB Gimbal Check Initiated | Booster: PRESS SRB Gimbal Check | 10:30
C | -- | 0 | 0:00 | ### | Capcom | 20 seconds |  | 10:30
C | -- | 0 | 0:00 | ### | MAX | Sound Suppression Activated | Max: PRESS LC-39A Snd Supp | 10:30
C | -- | 0 | 0:00 | ### | Capcom | 15 seconds |  | 10:30
C | -- | 0 | 0:00 | ### | Booster | LH2 Bleed Vlv Closed | Booster: PRESS LH2 Bleed Vlv | 10:30
C | -- | 0 | 0:00 | ### | Capcom | 10 seconds |  | 10:30
C | -- | 0 | 0:00 | ### | Booster | Go for Main Engine Start | Booster: PRESS H2 Burnoff | 10:30
C | -- | 0 | 0:00 | ### | Capcom | Main Engine Start, 5,4,3,2,1, Booster Ignition, Liftoff | Booster: Check for following: ~IDL greenlines on SSME 1,2,3 ~>90%Throttle on MacMECO Call an immediate Abort and PRESS SSME Shtdn 1,2,3 if any of these is off-nominal | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
| -- | [6 empty] | 10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30
10:30