Swim Meet To Do List


√
Task Description
Assigned To:
Due

Date


Check pool availability with Facility




Submit Request for Meet form to New England Swimming (NES) along with

Meet Announcement









cover sheet (dates, times, facility, safety, scoring, seeding, lodging, map, entry

requirements, phone #'s)





schedule of events (qualifying times)





entry cover sheet





entry form





Receive Approval for Meet and application for Sanction from NES





Submit Application for Sanction and send to NES along with dollars: $200 returnable





deposit + $15/day of the meet (Complete a separate sanction request and send an





additional $15 to conduct time trials at a meet)






Obtain contract from facility. Confirm all components.






Mail Meet Announcement to Web Site (NES does mailing for Championships)





Contract with facility for equipment





Concession, lounge, office, locker space





Tables and chairs





Parking barrier





Trash and can barrels





Safety Marshals





How to leave the pool at end of meet (level of c1ean-up, how to lock up)





Timing System: set up and take down





Other needed equipment I space





Contract with swimsuit vendor for space at meet





Identify Referee for meet. Ref can help find Officials for the meet






Arrange for computer at meet





Reserve hotel rooms if needed (referee, team block discounts)






Letter to parents emphasizing need for considerable help





Gather phone numbers for all parents





Register  marshals, managers with USS





Find Volunteers for the meet - Identify positions needed





Referee





Starter





Stroke and Turn





Warm-up pool marshals





Warm-up marshals (move to other positions once the meet starts)





Backup timer





Head timer





Computer results entry





Timing System I Announcer





Timing (2/lane)





Runner/Poster





Awards (sticking labels, sorting)





Concessions





Concessions coordinator for session/day





Admissions





Parking



√
Task Description
Assigned To:
Due

Date


Order awards for the meet (NES places order for Championship meets)




Order 3part relay cards from NES if needed




Order 3 part disqualification forms if needed




Arrange food concession needs




order food




arrange storage space




arrange for start up cash, especially quarters, ones




price signs




arrange for supplies / equipment (microwave, large coffee pots, extension cords)




Prepare computer program




Run set-up program




Enter events and qualifying  times




Enter records / age group cut times




Receive entries: Log in entries




team




date/time




$ to team ($ to NES if a championship meet)




$ over/under




Give list of participating teams to person finding officials




Enter entries into computer




Print out computer team entry




Print out timeline




Identify necessary cuts




Print draft heat sheet (check for obvious time typos/errors by looking at fastest




and slowest swimmers of each event)




Print list of # of swimmers by team by session and number of entries for last




events each session to use in assigning timing lanes




Copy computer entry to send back to the teams




Determine timing assignments based on participation, number of entries in last




events, other officials working the meet




Develop database of team information




Team name




Contact name, address, phone number, email




Coach name




Number of swimmers, entries, relays




Label layout to send out information




Team letter/name layout for program




Team entry layout of count of swimmers and entries




Mail coach information packets




Restate warm-up times, scratch procedures, other meet specific information




(much of it frau' meet announcement)




Directions to pool




Timing assignments




Copy of computer entry - mark cuts in red on that form




Arrange for cash at meet: start up cash, specially ones and quarters




concessions




admissions/programs




Entry Chair notifies teams of cuts




Print Final Entry sheets




Print final heat sheet




Print scratch sheets



√
Task Description
Assigned To:
Due

Date


Prepare Coaches' Packets




Programs (1 program per team)




Cover letter sent in Meet Info Packets




Scratch procedures (copy of entries)




Meal passes




Instructions for time trials and/or deck entries




Instructions for relay entries




Safety instructions




Check supplies for meet




stop watches (2/lane + 2 or more for back-up timer + extras)




batteries




clipboards




pencils




pencil sharpener




radio headsets




first aid supplies




tape of National Anthem




box of tractor feed paper for fixing system printer




4+ reams of paper for results computer




labels for awards




blank seed cards (for time trials)




DQ slips (3 part forms)




relay cards (3 part forms)




lap counters




bell for distance events




starter pistol and blanks




USS Accident forms




Correct count of medals and ribbons




Large water jug for pool office




grocery bags for each team for awards




Timer instructions (tape basic version to clipboards)




masking tape




rubber bands




small cooler for injury ice




tables for Admissions




signs and tape (stay out, location of lost & found, please dean-up trash)




duct tape




magic markers for impromptu signs




can of compressed air to use on touch pad plugs




Create Final Program




Create a cover page (different cover for different sessions if selling separately)




Prepare advertisements for copying




Welcome and safety message




Timing assignments




Insert final heat sheet




List of participating teams




Have copies made (warn copy shop in advance if need quick turnaround)




Large mailing envelopes for parents to buy results (have them address them at




the Admissions tables)




Create session specific programs




Enough copies for all officials that session (10-12?)




Create copies of programs to post on hallway and pool deck walls (3 if pre-seeded)




Print Out first session worth of seeding and timing sheets (just in case computer acts




up at the meet)



√
Task Description
Assigned To:
Due

Date



Arrange for food/munchies to be available in the pool office each session for workers





and coaches






Prepare official notebook for the meet





Original entries





Team list: coaches, contacts, phone numbers





Meet program





Letters sent to teams





USS Accident Forms





Timeline





Work Assignments





Timing Assignments




At 
the Meet





Day I





check for appropriate chairs, tables, barrels, parking barrels, timing system,





anything else provided by the Facility (check for everything before 4:30 to ensure





can get help if needed)





check that all equipment is working: timing system, microphone, tape deck





check National Anthem tape





Unload food and set up concession stand and admissions areas





Set up pool deck: chairs, tables, signs, computer, buttons, cones, counters





Post heat sheets (pre-seeded meets) in bleachers hallway and on pool deck





Post heat sheets (non pre-seeded meet) in two locations on pool deck





Post work assignments and timing assignment in pool office





Give a copy of work assignments to Concessions





 Timing System I Results Computer





Set-up computer and printers





Test label printer





During the Meet






 Timing System I Results Computer





Enter scratches





Seed first four events at least 20 minutes before meet is scheduled to start





Enter scratches by team





Run seeding: 4 copies of seedings, timer sheets





Post seedings in each pool





Give two copies of seedings to ref/head timer





Seed additional events as time and scratches allow




Other tasks during meet






Distribute meal passes to officials





Collect, separate, and deposit money





Make rounds to determine all is going well amongst all the workers, locker




rooms, and areas off-limits




Be available for coaches questions





Keep one set of medals available for the Awards Ceremony 





Distribute sodas to workers on deck 





Take full garbage bags to appropriate location 





Print and distribute copies of the results





one copy stays with the results computer as the official copy





one copy is posted in the stands





one copy is posted on the pool deck





one copy to NES verifier (Age Group championship meets only, so entries





can be verified during the meet)



√
Task Description
Assigned To:
Due

Date


End of Each Day




Clean deck, bleachers, lobby, locker rooms




Take full garbage bags to trash storage location




Lock all doors providing access to pool area bleacher doors, both locker rooms,




pool office, emergency exit)




Either ensure pool area is empty and lock doors behind you as you leave or




specifically tell the next user of the pool (who is there) that they now have control




of the pool.





End of Meet




Sweep stands




Collect lost & found (hold for a week or two then donate to a thrift shop)




Clean deck, bleachers, lobby, locker rooms




Take full garbage bags to trash storage location




Stack chairs and tables




Move facility furniture back in place




Either ensure pool area is empty and lock doors behind you as you leave or




specifically tell the next user of the pool (who is there) that they now have control




of the pool,




Post Meet




Deposit money: separate by admissions/programs/results, concessions, time




trial/deck entries




Print final results by age group and stroke (include high point results and time




trial results) 




Email final results to website.




Copy results on to computer disks for those teams that sent entries by disk




Label box and store timing sheets, tapes and results (must keep for a year)




CELEBRATE!




Thank you to parents




Copy and distribute results (mailing labels from database)






8 copies to NES




1 copy to each person who bought results




Debrief with coordinators to identify successes and areas to improve, make




suggestions on how to change




Complete Meet Summary/financial Report Form and submit to NES




Complete Self Evaluation Form and submit to NES




Complete file of meet information to keep for planning future meets




Revise To Do List for future meets




Identify changes to make for future meets






Check pool availability for next year




Toss final timing sheets, results and entries after one year



Page 1

