What is the Approval Process?

Project quality management ensures that there is adequate review of project deliverables at phase completion.  Approval is a formalized process ensuring that the appropriate levels of testing and review have been completed.

The approval process has been discussed separate from the development life cycle.  The process of ensuring that appropriate approvals are obtained is part of the management function and is not strictly a technical function.

The approval process ensures that each defined project phase and associated deliverables are successfully completed before beginning subsequent phases.  Management gets a comprehensive view of the current project status.  Information necessary to ensure that deliverables satisfy the specific business needs of the state organization is also received.  Project approval also allows management to reassess the direction of the project, as necessary, and to provide project planning updates, as required.

There are typically three types of approval processes.  The first, project plan approval has been addressed in Project Planning.  Approvals discussed in this section occur during the execution stage and include:

- Phase reviews

- Deliverable reviews

These approval processes are shown in the figures below.

Phase Approval Process

Deliverables Approval

The approval process takes place on two levels.  First, the technical teams agree that a phase has been completed, and then a phase completion meeting is held to formalize the event and move on to the next phase.

Documentation approval can also be formalized, but on a more limited scale, possibly among sub-sets of the project team.

For document approval, the project plan should contain a more detailed deliverable list that includes not only date items and WBS relationship, but also the name of the person(s) who must approve the document. The figure below provides a sample of how one project summarized this information.

### Sample Information Summary

| Document Name | Project Phase | To Be Approved by |
| --- | --- | --- |
| Project Plan Hardware Procurement & Install Plan Site Prep. and Facilities Plan Network Plan Test Plans Quality Plan Data Plan Training Plan Contingency Plan Pilot Implementation Plan Roll out and Cutover Plan Maintenance Plan Support Service Plan Turnover Plan Warranty Plan Backup and Recovery Plan Gap Analysis Report Implementation Recommendation Report Re-engineered Process flows Detailed Requirements Detailed Design Interface Design Document Training Curriculum Certifications | Phase 1-6 Startup Startup Startup Phase 1-6 Startup Phase 1-6 Phase 1-6 Phase 1-6 Gap Analysis Phase 1-6 Phase 1-6 Phase 1-6 Phase 1-6 Phase 1-6 Phase 1-6 Gap Analysis Phase 1-6 Phase 1-6 Startup Startup Phase 1 Phase 1-6 Phase 1-6 | Project Sponsor Steering Comm./Imp. Team Steering Comm./Imp. Team Steering Comm./Imp. Team Imp team/stakeholders Steering Comm./Imp. Team Imp. Team/stakeholders Imp. Team/stakeholders Imp. Team/stakeholders Steering Committee/Imp team/stakeholders Implementation Team Steering Comm./Imp. Team Steering Comm./Imp. Team Steering Committee Implementation Team Steering Comm./stakeholders Steering Committee Imp. Team Stakeholders/Exec Mgmt Imp. Team/stakeholders Imp. Team/stakeholders Implementation Team Imp. Team/stakeholders Imp. Team/stakeholders/Steering Committee |