## Project Change Control
PCR # | Description | Need by Date | Status | Complete Date | Priority | Release #
1 | Set up development site | 1999-05-21 | complete | 1999-06-01 | med | pre 1.1
2 | Give moderators admin view without admin update | 1999-05-31 | complete | 1999-06-15 | high | 1.1
3 | Correct response time for books, tools | 1999-06-15 | 1.2 |  | med | 1.2
4 | Correct error when deleting only recommended link | 1999-05-31 | complete | 1999-06-01 | med | 1.1
5 | Change color for time out statement | 1999-05-31 | complete | 1999-06-01 | med | 1.1
6 | Review and correct problems with not loading images | 1999-05-31 | 1.2 |  | med | 1.1
7 | Automatically test the links for recommended links when submitting | 1999-05-31 | complete | 1999-06-01 | med | 1.1
8 | Allow admin to unpublish items | 1999-05-31 | complete | 1999-05-25 | high | 1.1
9 | Sort books by Author last name | 1999-05-31 | complete | 1999-06-01 | high | 1.1
10 | Sort books by Title | 1999-05-31 | 1.2 |  | high | 1.1
11 | Add/maintain book review process` | 1999-05-31 | 1.2 |  | high | 1.1
12 | Maintain/update/publish screen in interest areas should be like books and tools | 1999-05-31 | 1.2 |  | high | 1.1
13 | Need an "all" select on the tools platforms, languages etc | 1999-05-31 | complete | 1999-06-01 | high | 1.1
14 | Hide language fields if there is only one language | 1999-05-31 | complete | 1999-06-01 | high | 1.1
15 | Add submitter information to the interest area displays | 1999-05-31 | complete |  | high | 1.1
16 | Add unreviewed selection for moderators | 1999-05-31 | complete |  | high | 1.1
17 | Add a feedback feature to tools and books for audience to suggest additional books and tools | 1999-05-31 | complete |  | high | 1.1
18 | Add an email function for audience to communicate with moderators | 1999-05-31 | complete |  | high | 1.1
19 | Add moderator approval button when moderators are submitting items | 1999-05-31 | complete |  | high | 1.1
20 | Add same edits to the update functionality as exists for the add funcitonality | 1999-05-31 | in test | 1999-06-01 | high | 1.1
21 | Change the button name from "tools" to "category" in the tools search frame | 1999-05-31 | in test | 1999-06-01 | high | 1.1
22 | Change the button name from "tools" to "category" in the book search frame | 1999-05-31 | in test | 1999-06-01 | high | 1.1
23 | Change the words in the tools frame as shown | 1999-05-31 | in test | 1999-06-01 | high | 1.1
24 | Change the words in the books frame as shown | 1999-05-31 | in test | 1999-06-01 | high | 1.1

## Sheet2
Number | Description | Need by date | Status | Complete Date | Priority | Release #
3 | Correct response time for books, tools | 1999-06-15 | 1.3 |  | med | 1.2
6 | Review and correct problems with not loading images | 1999-05-31 | 1.3 |  | med | 1.1
10 | Sort books by Title | 1999-05-31 | 1.3 |  | high | 1.1
11 | Add/maintain book review process` | 1999-05-31 | 1.2 |  | high | 1.1
11a | Change "buy" button on book table to "click to purchase" | 1999-06-15 | 1.2 |  | high | 1.2
11b | Add click in recommendation column of book table to go to review information | 1999-06-15 | 1.2 |  | high | 1.2
11c | Allow moderator to approve book reviews | 1999-06-15 | 1.2 |  | high | 1.2
12 | Maintain/update/publish screen in interest areas should be like books and tools | 1999-05-31 | 1.2 |  | high | 1.1
16 | Add unreviewed selection for moderators | 1999-05-31 | 1.2 |  | high | 1.1
19 | Add moderator approval button when moderators are submitting items | 1999-05-31 | 1.2 |  | high | 1.1
20 | display data utilizing carriage returns | 1999-06-15 | 1.2 |  | high | 1.2
21 | Title in FAQ's should be "Question" the description should be "answer" | 1999-06-15 | 1.2 |  | high | 1.2
22 | Library has no attachments in the configuration mgmt section of the interest area | 1999-06-15 | 1.2 |  | high | 1.2
23 | Add Web/e-business section to the IA | 1999-06-15 | 1.2 |  | high | 1.2
24 | Correct the formatting in the description fields thru out the site | 1999-06-15 | 1.2 |  | high | 1.2
25 | drop the date stamp from the frame listing section entries for all interest area sections except the forums. | 1999-06-15 | 1.2 |  | high | 1.2
26 | The URL's should be hot links whenever included in the text of the item | 6.15.99 | future |  | high | 1.2

## Sheet3
SQL 7 conversion
DB Design cleanup/performance
No feature updates
Build script to move code from test to prod
code clean up