## Chapter 2:  FAM Process Description

| #### Introduction | This chapter contains process descriptions for the activities of the FAA-iCMM Appraisal Method (FAM). |
| --- | --- |

| #### In this section | The following process descriptions are provided. |  |  |
| --- | --- | --- | --- |
|  | ID | Activity Name | See Page |
|  | 2.1 | Plan and Prepare for the Appraisal | 2-3 |
|  | 2.1.1 | Obtain Sponsor Commitment | 2-4 |
|  | 2.1.2 | Select Appraisal Scope | 2-7 |
|  | 2.1.3 | Select Appraisal Team | 2-10 |
|  | 2.1.4 | Plan Appraisal Details | 2-13 |
|  | 2.1.5 | Orient Participants | 2-17 |
|  | 2.1.6 | Train Team | 2-20 |
|  | 2.1.7 | Administer Questionnaire | 2-23 |
|  | 2.1.8 | Develop Exploratory Questions | 2-25 |
|  | 2.2 | Conduct Appraisal | 2-29 |
|  | 2.2.1 | Conduct Opening Meeting | 2-30 |
|  | 2.2.2 | Conduct Interviews | 2-32 |
|  | 2.2.3 | Review Documentation | 2-36 |
|  | 2.2.4 | Consolidate Data | 2-40 |
|  | 2.2.5 | Develop Draft Findings | 2-44 |
|  | 2.2.6 | Present Draft Findings | 2-47 |
|  | 2.2.7 | Develop Ratings | 2-50 |
|  | 2.2.8 | Develop Final Briefing | 2-55 |
|  | 2.2.9 | Brief Sponsor | 2-57 |
|  | 2.2.10 | Present Final Briefing | 2-60 |
|  | 2.2.11 | Conduct Wrap-Up | 2-63 |
|  | 2.3 | Report Results | 2-66 |
|  | 2.3.1 | Prepare and Deliver Appraisal Report | 2-67 |
|  | 2.3.2 | Manage Records | 2-69 |

## Chapter 2: FAM process description, continued

| #### Process descriptions | All activity descriptions are formatted the same, containing the paragraphs that are described in Table 2-1. Detailed guidance for how to perform the activities and training materials are provided separately. |  |
| --- | --- | --- |
|  | Block Title | Description |
|  | Purpose | The purpose for this phase or activity. |
|  | Summary description | A summary of the work performed during the activity. |
|  | Entry criteria | The conditions or decision to start. |
|  | Exit criteria | A description of the decision-making criteria to determine if the phase or activity has been completed. |
|  | Roles | The roles involved in the phase or activity and a summary of their responsibilities. |
|  | Inputs | The input artifacts needed to perform the activity. |
|  | Steps | The list of steps or tasks and brief guidance to perform each step. |
|  | Outputs | The output artifacts of this phase or activity that may be checked for compliance. |
|  | Typical duration/effort | The measurements collected and how to collect them as part of improvement of the process.  Typical calendar duration  Typical effort (team or staff hours to perform the activity) Appraisal work product measurements may be collected as applicable. |
|  | Notes | Notes that do not fit in any of the other categories including references, or guidance. |

Table 2-1. Process Description Format.

### 2.1  Plan and Prepare for the Appraisal

| #### Purpose | The purpose of the Plan and Prepare for the Appraisal phase is to prepare the sponsor, the appraisal team, and the organization (appraised entity) for the appraisal activities. |
| --- | --- |

| #### Summary description | Plan and Prepare for the Appraisal includes activities to achieve the following  The sponsor commits to the resource and action requirements for the appraisal  The team and other participants are selected, trained or oriented, and commit to perform the appraisal  The organization provides preliminary data to the team for analysis, and the team analyzes the data and prepares for the interactive data gathering, analysis, feedback, and reporting activities. |
| --- | --- |

### 2.1.1 Obtain Sponsor Commitment

| #### Purpose | The purpose of Obtain Sponsor Commitment is to establish the appraisal goals, the sponsor's commitment to funding and outcomes, and the appraisal constraints. |
| --- | --- |

| #### Summary description | Obtain Sponsor Commitment involves meeting with the sponsor(s) of the appraisal to provide an understanding of the concepts of the FAA-iCMM and the FAA-iCMM appraisal method (FAM), engaging the sponsor in dialogue to determine the goals for the appraisal and the needed resources, to include personnel and funding, for the appraisal activities. A primary outcome of obtaining sponsor commitment is assurance that the sponsor understands his/her role in the appraisal. |
| --- | --- |

| #### Entry criteria |  Invitation to participate in the decision to perform an appraisal |
| --- | --- |

| #### Exit criteria |  Appraisal goals established.  Appraisal variation selected.  Sponsor commitment to provide appraisal resources obtained.  Sponsor commitment to appropriate behavior during the appraisal obtained. - Appraisal team leader selected |
| --- | --- |

| #### Roles | Table 2-2 lists the roles involved in this step. |  |
| --- | --- | --- |
|  | Role | Summary |
|  | Sponsor | Engages in dialogue with appraisal team leader and/or advocate to understand appraisal context and set appraisal goals; commits resources for the appraisal. Selects/approces appraisal team leader. |
|  | Appraisal advocate | Establishes link between sponsor, appraisal team leader, and potential appraisal participants. |
|  | Appraisal team leader | Provides sponsor with information needed to make a commitment decision on the appraisal. |

Table 2-2.  Participants for Obtain Sponsor Commitment.

continued on next page

2.1.1  Obtain sponsor commitment, continued

| #### Inputs |  Appraisal information or presentation  Examples of schedules and levels of effort for appraisals |
| --- | --- |

| #### Steps | Table 2-3 shows the steps for this activity. |  |
| --- | --- | --- |
|  | Step | Description |
|  | Understand the customer’s problem | Identify sponsor interests and business goals that appraisal could address. |
|  | Propose appraisal solution | Brief sponsor on appraisal context in the improvement cycle, outcomes, type and tailoring options and what they provide and do not provide, approximate schedule, and expectations of the sponsor’s participation. |
|  | Agree on basics | Agree on appraisal type and sponsor role, and assign the appraisal team leader, an organizational appraisal representative and a site coordinator to make arrangements. |
|  | Record commitments | Document the agreements. |

Table 2-3.  Steps for Obtain Sponsor Commitment.  Steps for Analyze Questionnaire.;

| #### Outputs |  Documented agreement about appraisal goals, type, funding, sponsorship for the general resources needed, and a tentative schedule for the planning and conduct of the appraisal. |
| --- | --- |

| #### Typical duration/ effort |  Typical calendar duration: Two hours to several weeks  Typical level of effort: 1 hour to a day |
| --- | --- |

2.1.1 Obtain sponsor commitment, continued

| #### Notes | This is a go/no-go decision point. If sponsor commitment for the appraisal is not obtained, no further steps related to FAM should be performed. The Appraisal Team Leader (ATL) is normally the person who is brought in by the appraisal advocate to initiate appraisal action. The ATL is typically an approved lead appraiser in the FAM. The sponsor typically approves the ATL selection at this time. The Organizational Appraisal Representative (OAR) and site coordinator may be identified at this time. If not identified, the appraisal advocate can serve as the OAR until one is identified. The site coordinator may be identified at this time if necessary. However, the site coordinator is normally assigned once the appraisal period requires logistics support. |
| --- | --- |

### 2.1.2  Select Appraisal Scope

| #### Purpose | The purpose of Select Appraisal Scope is to establish the appraisal scope to meet the goals established with the sponsor for the appraisal. |
| --- | --- |

| #### Summary description | Select Appraisal Scope involves determining the FAA-iCMM process areas and capability levels and the set of projects to be selected from the organization. In addition, a preliminary appraisal plan is produced. |
| --- | --- |

| #### Entry criteria |  Sponsor commitment to fund and perform appraisal obtained. |
| --- | --- |

| #### Exit criteria |  Preliminary appraisal plan developed including  aspects of the model to be included in the appraisal  projects and groups to provide participants - OAR and site coordinator identified |
| --- | --- |

| #### Roles | Table 2-4 lists the roles involved in this activity. |  |
| --- | --- | --- |
|  | Role | Summary |
|  | Site coordinator or Organizational appraisal representative | Checks on schedules, lead times, potential participants availability constraints to establish schedule and makes tentative arrangements for the appraisal. Administers project/organization questionnaires. |
|  | Appraisal team leader | With affected management, determines the projects, process areas, and capability levels to include in the appraisal. Drafts feasible schedules to perform the appraisal and proposes one as part of the preliminary plan. |
|  | Sponsor | Provides appropriate input on organization, goals, and scope in terms of projects to include and applicable parts of the model. |

Table 2-4.  Participants for Select Appraisal Scope..  Participants for Select Appraisal Parameters.;

continued on next page

### 2.1.2  Select appraisal scope, continued

| #### Inputs |  Sponsor’s appraisal and business goals (from previous activity)  FAA-iCMM  Organization chart  Appraisal plan template |
| --- | --- |

| #### Steps | Table 2-5 shows the steps for this activity. |  |
| --- | --- | --- |
|  | Step | Description |
|  | Administer project and/or organization questionnaire | Collect project/organization data to help determine appraisal scope, if necessary. |
|  | Identify appraisal scope | Based on the business goals of the organization, identify the model process areas and capability levels needed, appraisal method tailoring to accomplish the appraisal goals, and life cycle coverage. |
|  | Identify organization scope | From the appraisal scope, work with the advocate or sponsor to identify the affected parts of the enterprise to be included in the appraisal, and designate those not to be included. |
|  | Make preliminary arrangements | Identify the organizational appraisal representative and site coordinator if not done in previous activity (2.1.1). Produce a list of potential participants from projects and functional groups within the organization’s projects scope. Identify possible schedules and other tentative arrangements for the appraisal. |
|  | Document preliminary plan | Draft a plan for the appraisal. |

Table 2-5.  Steps for Select Appraisal Scope

### 2.1.2 Select appraisal scope, continued

| #### Outputs | Preliminary appraisal plan to include:  goals  appraisal scope description  appraisal method  description of entity being appraised  tentative schedule  estimated costs  candidate organizational participants |
| --- | --- |

| #### Typical duration/ effort |  Typical calendar duration: One to two weeks, depending on complexity of tailoring required, and sponsor’s prior experience with appraisals  Typical level of effort: 1 to 8 staff hours |
| --- | --- |

| Notes |  The site coordinator performs all logistics functions. However, if a site coordinator is not identified at this time the organizational appraisal representative can perform these duties. - Project and/or organization data collected may be used to orient appraisal team or for help in developing exploratory questions. |
| --- | --- |

### 2.1.3 Select Appraisal Team

| #### Purpose | The purpose of Select Appraisal Team is to select an appraisal team with the capability and experience to conduct the appraisal. |
| --- | --- |

| #### Summary description | Team members are identified, invited, and scheduled, and commit to participating in this activity. |
| --- | --- |

| #### Entry criteria |  Preliminary Appraisal Plan  List of potential appraisal participants - OAR, ATL and site coordinator selected |
| --- | --- |

| #### Exit criteria |  Appraisal team members selected.  Sufficient potential participants to cover the appraisal scope identified. |
| --- | --- |

| #### Roles | Table 2-6 lists the roles involved in this activity. |  |
| --- | --- | --- |
|  | Role | Summary |
|  | Appraisal advocate and/or sponsor and/or Organizational appraisal representative | Provides the appraisal team leader and/or site coordinator with organization, project, and potential participant knowledge. Approves and communicates desired participants through the management chain to encourage their ability to participate. |
|  | Appraisal team leader | Guides or approves selection of team to achieve coverage of the appraisal scope. |
|  | Site coordinator | Makes contact and finds availability of potential team members, notifies them, and schedules the appraisal activities. |

Table 2-6.  Participants for Select Appraisal Team..  Participants for Select Appraisal Parameters.;

| #### Inputs |  Organizational elements selected to participate in the appraisal (from previous activity) |
| --- | --- |

### 2.1.3  Select appraisal team, continued

| #### Steps | Table 2-7 shows the steps for this activity. |  |
| --- | --- | --- |
|  | Step | Description |
|  | Identify team member candidates | Brainstorm potential team members. |
|  | Select team members | Invite candidates to serve on the team. Get agreements to serve and ensure that this will be the priority for the team members during the appraisal period. Come to agreement with the team members about the priority and need to participate in every team activity barring family emergencies. Identify individuals for team roles. |

Table 2-7.  Steps for Select Appraisal Team.  Steps for Analyze Questionnaire.;

| #### Outputs |  Appraisal team member role commitments secured  Cross-reference matrix of potential participants by process area or project to demonstrate coverage of organization and model subset |
| --- | --- |

| #### Typical duration/ effort |  Typical calendar duration: Site coordinator: 1-4 weeks, Others: 1-2 hours  Typical level of effort: 2 to 16 staff hours |
| --- | --- |

### 2.1.3  Select appraisal team, continued

| #### Notes | The ATL must be selected by this time if not selected during Obtain Sponsor Commitment. Team size is typically 5 to 8 members with a minimum of 4 and a maximum of 12. This includes the appraisal team leader and organizational appraisal representative, but excludes the site coordinator who is not a team member. The majority of team members should have at least five years of appropriate functional experience and the team should have a total of 25 or more years of total functional experience. Team members also should each have a minimum of 1 year with the organization with the team having a total of at least 25 years. At least one member should have at least 6 years of management experience with a total of ten years for the team. Those participating should include opinion leaders, those who will have to make the changes indicated, those who know what typically happens on, and in the organizational infrastructure that supports, projects, and those who manage projects and support groups. Observers are not recommended, but if permitted, must be committed to non-intrusive behavior, and there should not be more than two. More detailed definitions of desirable qualifications for the roles on an appraisal are provided in Table 1-4, Chapter 1. |
| --- | --- |

### 2.1.4  Plan Appraisal Details

| #### Purpose | The purpose of Plan Appraisal Details is to produce and approve an appraisal plan. |
| --- | --- |

| #### Summary description | Plan Appraisal Details involves filling in the details, scheduling and staffing, documenting and approval of the plan. |
| --- | --- |

| #### Entry criteria |  Appraisal scope and sufficient and appropriate staff identified. |
| --- | --- |

| #### Exit criteria |  Appraisal plan approved. |
| --- | --- |

| #### Roles | Table 2-8 lists the roles involved in this activity. |  |
| --- | --- | --- |
|  | Role | Summary |
|  | Site coordinator | Confirms logistics details for the appraisal. |
|  | Appraisal team leader | Develops plan and documentation. Leads appraisal risk assessment activities. Produces questionnaire(s). |
|  | Sponsor | Approves appraisal plan. |

Table 2-8.  Participants for Plan Appraisal Details.

| #### Inputs |  Preliminary appraisal plan (Appraisal goals, budget, scope, and potential staffing from previous activities)  Appraisal plan template(Toolkit) |
| --- | --- |

continued on next page

### 2.1.4  Plan appraisal details, continued

| #### Steps | Table 2-9 shows the steps for this activity. |  |
| --- | --- | --- |
|  | Step | Description |
|  | Finalize participants | Final selection of willing, available, and appropriate participants, and obtaining commitments to participate from them. |
|  | Finalize schedule | Finalizes the schedule with the participant selection and commitments, and confirm or make arrangements for workspace, supplies, support, etc. |
|  | Finalize budget | Estimate all costs of all resources. |
|  | Identify appraisal risk | The risks associated with conducting the appraisal should be identified with appropriate mitigation actions or plans. |
|  | Document plan | Document the plan. |
|  | Develop questionnaire(s) | Develop and append to the appraisal plan the master questionnaire(s) and a cover sheet describing any tailoring performed, relationship to the appraisal scope, and/or rationale for questionnaire subsets allocated to specific respondents, such as Configuration Management PA questions for a CM practitioner. |
|  | Request documentation | Identify documentation and other artifacts that demonstrate that practices in the scope of the model are being performed. Request copies from probable users. Establish the documentation library and designate a team member as data manager to manage the documentation and artifacts submitted. |
|  | Approve plan | Review, adjust, and approve plan, and communicate plan details to those affected. |

Table 2-9.  Steps for Plan Appraisal Details.  Steps for Analyze Questionnaire.;

### 2.1.4  Plan appraisal details, continued

| #### Outputs |  Approved appraisal plan, which includes - goals  scope of the model  scope of the organization (projects and functions to be included)  budget  tasks and schedule  team members and other participants  logistics including  meeting rooms and supplies,  equipment  support staff availability  identification of all appraisal reports  the recipients of both the oral and written appraisal reports  appraisal risks and mitigations  Questionnaire(s)  Documentation or artifact requests |
| --- | --- |

| #### Typical duration/ effort |  Typical calendar duration: Two to six weeks, depending on the complexity of the appraisal plan  Typical level of effort: 4 staff hours to a staff week |
| --- | --- |

### 2.1.4 Plan appraisal details, continued

| #### Notes | This is when the actual schedule for the Conduct Appraisal phase is produced. See the Toolkit Appraisal Checklist for details on preparing for the logistics of an appraisal. The questionnaire used in the appraisal is developed based on the model scope, organizational scope (projects and other participants), and background demographics that can help improve the method and model when feedback have been collected and are compared to other appraisal instances. The questionnaire typically includes  PA goals achieved (to be answered by leads)  PA practices performed (to be answered by practitioners) The organization and project questionnaires typically include organization, project and infrastructure descriptions, products provided to customers, equipment (tools), geographic dispersion, and customer identification or characteristics (to be completed by an appropriate organization member). Any useful documents, such as policies, process descriptions (often in training materials), standards, even meeting minutes or action item lists, may be requested, collected, organized, and stored by the site data manager. An example request form for such materials is in the Toolkit with the schedule forms for participants and team members. |
| --- | --- |

### 2.1.5  Orient Participants

| #### Purpose | The purpose of Orient Participants is to prepare the appraisal participants to perform their information sharing roles, especially to make the participants as comfortable as possible with the “what, why, and how” of the appraisal process so that they will participate appropriately. This activity may be combined with or replace the opening meeting (see Activity 2.2.1). |
| --- | --- |

| #### Summary description | The orientation begins with an overview of the appraisal plan including the appraisal scope, with an optional overview of the model content and structure. The what, why, and how of the appraisal, with expected outcomes, are provided along with a question and answer session. Questionnaires may be administered immediately following this activity (see Activity 2.1.7). |
| --- | --- |

| #### Entry criteria |  Appraisal participants identified and invited to attend |
| --- | --- |

| #### Exit criteria |  Appraisal participants appear to be willing and able to participate in the appraisal process. |
| --- | --- |

| #### Roles | Table 2-10 lists the roles involved in this activity. |  |
| --- | --- | --- |
|  | Role | Summary |
|  | Appraisal team leader | Leads the team through the model and appraisal method and answers any questions. |
|  | Organizational appraisal representative | Provides orientation on the organization and its products. |
|  | Participants | Learn model and appraisal method and receive questionnaire if provided at this time. |

Table 2-10. Participants for Orient Participants

continued on next page

2.1.5  Orient participants, continued

| #### Inputs |  Appraisal plan (previous activity)  Template of briefing materials (tailor from Toolkit team training materials)  Questionnaire (see 2.1.4 and 2.1.7) |
| --- | --- |

| #### Steps | Table 2-11 shows the steps for this activity. |  |
| --- | --- | --- |
|  | Step | Description |
|  | Conduct orientation briefing | Conduct the orientation briefing. The briefing includes the purpose and scope of the appraisal, typical outputs, the appraisal plan, confidentiality rules, and optionally, the model content and format. |

Table 2-11.  Steps for Orient Participants

| #### Outputs |  Briefing slides  Recorded questions and answers |
| --- | --- |

| #### Typical duration/ effort |  Typical calendar duration: 1-2 hours  Typical level of effort: 1-2 hours |
| --- | --- |

2.1.5  Orient participants, continued

| #### Notes | This activity reduces participant concerns by providing open and candid descriptions of the what, how, and why of the appraisal, together with a question and answer session. The orientation is typically a 1-2 hour activity which overviews the FAA-iCMM and the appraisal method. Orientation participants include all personnel who will be involved in interviews and any personnel who are interested in appraisal findings and will be involved in post appraisal improvement activities. The orientation briefing should consider for inclusion: the purpose and objectives of the appraisal, FAA-iCMM, confidentiality rules, the activities of appraisal method, and subsequent possible activities. This activity is especially important for organizations new to appraisals. It may be combined with or replace the Opening Meeting (see Activity 2.2.1). The questionnaire is typically administered to designated appraisal participants immediately following this activity. See Activity 2.1.7. |
| --- | --- |

### 2.1.6  Train Team

| #### Purpose | The purpose of Team Training is to prepare the appraisal team to perform its role in the appraisal process. |
| --- | --- |

| #### Summary description | This is a necessity for the appraisal team to understand the model, be able to perform the appraisal method, and build teamwork to enhance performance. Team training begins with one or more community-building exercises, an orientation on the organization and its products , an overview or detailed training on the model structure and content, and practice using the appraisal method techniques. |
| --- | --- |

| #### Entry criteria |  Appraisal team members identified and scheduled to attend |
| --- | --- |

| #### Exit criteria |  Appraisal team understands use of FAA-iCMM in appraisal context.  Appraisal team understands how to perform their roles.  Appraisal team commits to perform the appraisal as structured in the appraisal plan. |
| --- | --- |

| #### Roles | Table 2-12 lists the roles involved in this activity. |  |
| --- | --- | --- |
|  | Role | Summary |
|  | Appraisal team leader | Leads the team through the model and appraisal method training and answers any questions. |
|  | Organizational appraisal representative | Provides orientation on the organization and its products. |
|  | Appraisal team members | Learn model and appraisal method, participate in team-building, and practice appraisal techniques. |

Table 2-12. Participants for Team Training

continued on next page

2.1.6  Train team, continued

| #### Inputs |  Appraisal plan (previous activity)  Tailored method (previous activity)  Training materials |
| --- | --- |

| #### Steps | Table 2-13 shows the steps for this activity. |  |
| --- | --- | --- |
|  | Step | Description |
|  | Conduct team-building | The appraisal team leader leads the team in a team-building exercise; at the very least, all team members introduce themselves. |
|  | Provide overview | A general overview of the model, appraisal method, confidentiality rules, and a questions and answers session for all participants may be held at the outset. are discussed This may occur as a part of the opening orientation meeting. |
|  | Provide organizational orientation | Present organizational and product overview. |
|  | Review FAA-iCMM | Present the salient features of the model and its use in appraisal and discuss them with the team. |
|  | Review FAM | Explain each step in the appraisal process. Describe the roles with particular emphasis on behavior and procedures to be used. Describe the techniques that will be used, and lead the team through exercises to practice the techniques. |

Table 2-13.  Steps for Team Training

| #### Outputs |  Team training materials (exercise outputs useful for improvements)  Trained Team |
| --- | --- |

| #### Typical duration/ effort |  Typical calendar duration: 3 days  Typical level of effort: 3 team days |
| --- | --- |

2.1.6  Train team, continued

| #### Notes | This step ensures that the appraisal team understands the basic flow of the appraisal activities and their responsibilities throughout the Conduct Appraisal, Report Results, and Post-Appraisal phases. See the Toolkit for training support materials and tools such as the Appraisal Checklist. |
| --- | --- |

### 2.1.7  Administer Questionnaire

| #### Purpose | The purpose of Administer Questionnaire is to collect data on the practices and goal achievement of the organization and demographics that might affect organizational performance. |
| --- | --- |

| #### Summary description | Administer Questionnaire involves administering and collecting questionnaires, summarizing results from the questionnaire, collecting documentation and artifacts that demonstrate that the organization is performing practices, and collecting instruments used to profile the organization. The questionnaire may be administered as part of the orientation of participants who will be involved in the appraisal in Section 2.1.5, but must be done before developing exploratory questions (Section 2.1.8). |
| --- | --- |

| #### Entry criteria |  Questionnaires  Supporting documentation |
| --- | --- |

| #### Exit criteria |  Project profile information recorded.  Filled-in questionnaires recorded.  Documentation received and filed |
| --- | --- |

| #### Roles | Table 2-14 lists the roles involved in this activity. |  |
| --- | --- | --- |
|  | Role | Summary |
|  | Appraisal participants selected to complete a questionnaire | Provide data on projects and the organization via questionnaires. |
|  | Organizational appraisal representative or Site Coordinator | Arranges questionnaire administration, and collects any documentation. |
|  | Appraisal team leader or Organizational appraisal representative | Conducts the questionnaire administration. Answers respondents’ questions. |
|  | Data Manager | Organizes documentation collected. |

Table 2-14.  Participants for Collect Initial Data..  Participants for Collect Questionnaire Data.;

### 2.1.7 Administer Questionnaire, continued

| #### Inputs |  Questionnaire (previous activity)  Questionnaire instructions  Data recording and summarizing tool |
| --- | --- |

| #### Steps | Table 2-15 shows the steps for this activity. |  |
| --- | --- | --- |
|  | Step | Description |
|  | Collect documentation | Collect identified documentation from project contacts. |
|  | Administer the questionnaire | Distribute the questionnaire to all designated participants. |
|  | Collect questionnaires | Collect the questionnaires and secure them. |
|  | Summarize data | Transcribe or summarize the questionnaire data onto the summary medium. Examine and summarize practice or goal evidence from documentation review on the summary medium. |

Table 2-15.  Steps for Collect Initial Data..  Participants for Collect Questionnaire Data.;

| Outputs |  Questionnaire responses  Summarized questionnaire and documentation review data |
| --- | --- |

| #### Typical duration/ effort |  Typical calendar duration: 1-5 days  Typical level of effort: 1-4 participant hours plus 4-8 site coordinator hours |
| --- | --- |

### 2.1.7 Administer Questionnaire, continued

| #### Notes | The questionnaire covers the practices of the FAA-iCMM. Its results are used to focus interview data gathering during the appraisal. The questionnaires may be administered in various ways:  during the orientation meeting  one or more face-to-face meetings  electronically  fax response  mail-ins The questionnaire is typically distributed to the group at the end of participant orientation. The responses must be collected in a timely manner. Typically the questionnaires are administered during the same session as the orientation meeting. |
| --- | --- |

### 2.1.8  Develop Exploratory Questions

| #### Purpose | The purpose of Develop Exploratory Questions is to prepare the exploratory questions for use in the data gathering interviews conducted during the appraisal process. |
| --- | --- |

| #### Summary description | First, an analysis of the questionnaires is performed, based on the scope of the appraisal and other factors such as the expected maturity level of the organization. Questions are developed to facilitate the appraisal team in the data gathering (interview and document review process). The questions are targeted towards the level and area of responsibility of the participants. Training materials, or project-specific data such as plans, meeting agendas, or action item lists that have been collected may be reviewed and used to support exploratory question development and corroborate questionnaire answers. |
| --- | --- |

| #### Entry criteria |  Questionnaire responses summarized  Documentation received. |
| --- | --- |

| #### Exit criteria |  Exploratory questions and data requests are prepared for each process area and interview session. |
| --- | --- |

| #### Roles | Table 2-16 lists the roles involved in this activity. |  |
| --- | --- | --- |
|  | Role | Summary |
|  | Appraisal team leader | Leads the team in the process. Provides guidance in the analysis of the questionnaires and formulation of exploratory questions. |
|  | Organization appraisal representative | Translate model jargon to site terms and concepts in the EQs. |
|  | Appraisal team | Develops and agrees upon a set of initial questions and follow-up questions for the data gathering process. Also prepares "listen fors" for use during interview sessions. |

Table 2-16.  Participants for Develop Exploratory Questions..  Participants for Analyze Questionnaire.;

2.1.8  Develop exploratory questions, continued

| #### Inputs |  Template for Exploratory Questions (Toolkit)  Example Exploratory Questions worksheets by PA (Toolkit)  Summarized questionnaire data  Summarized documentation review data |
| --- | --- |

| #### Steps | Table 2-17 shows the steps for this activity. |  |
| --- | --- | --- |
|  | Step | Description |
|  | Review project profiles and documentation | The project profiles that were collected during the orientation process are reviewed. The appraisal team reviews documentation that may have been requested or provided to the team. |
|  | Analyze questionnaire responses | The appraisal team reviews the questionnaires in preparation for developing questions. The questions are reviewed based on the scope of the appraisal and organizational factors such as level of maturity. |
|  | Develop exploratory questions | The appraisal team generates exploratory questions and “listen fors” for each PA sorted by interview session. Lead in questions for each interview session should be identified. Once the questions are developed they should be transcribed into an appropriate form, and copies should be made for each team member. |

Table 2-17.  Steps for Develop Exploratory Questions.

| Outputs |  Documented exploratory questions and “listen fors” by PA or interview session |
| --- | --- |

continued on next page

2.1.8  Develop exploratory questions, continued

| #### Typical duration/ effort |  Typical calendar duration: 1 - 4 hours  Typical level of effort: 1 - 4 team hours |
| --- | --- |

| #### Notes | The develop exploratory questions process should be conducted before the on-site period. A team may request and use program documentation to aid the process to develop exploratory questions. Open-ended questions should also be developed. |
| --- | --- |

2.2 Conduct Appraisal

| #### Purpose | The purposes of the Conduct Appraisal phase are to obtain data about the entity being appraised, consolidate that data, develop ratings and present appraisal findings. |
| --- | --- |

| #### Summary description | Conduct Appraisal includes 11 activities as depicted below. |
| --- | --- |

### 2.2.1 Conduct Opening Meeting

| #### Purpose | The purposes of Conduct Opening Meeting are to describe the appraisal process to the sponsor and all appraisal participants; to review the appraisal schedule for them; and to give the sponsor an opportunity to express support for the appraisal activities. |
| --- | --- |

| #### Summary description | Conduct Opening Meeting involves gathering all the appraisal participants together, along with the sponsor or customer of the appraisal (depending on appraisal context), to describe the appraisal process, review the appraisal schedule, and publicly affirm the sponsor's commitment to the appraisal and the subsequent process improvement activities. |
| --- | --- |

| #### Entry Criteria | - Completed Appraisal Plan and decision to proceed with appraisal |
| --- | --- |

| #### Exit criteria | • Opening briefing delivered. • Questions of appraisal participants answered. |
| --- | --- |

| #### Roles | Table 2-18 lists the primary roles involved in this process element and a summary of their activity during this process. |  |  |  |
| --- | --- | --- | --- | --- |
|  |  | Role | Summary |  |
|  |  | Organization appraisal representative | Welcomes participants and introduces sponsor and appraisal team leader. |  |
|  |  | Sponsor | Shows management support for the appraisal and subsequent process improvement activities. Encourages active involvement by appraisal participants. |  |
|  |  | Appraisal team leader | Presents brief overview of the model and appraisal process. |  |
|  |  | Site coordinator | Presents schedules and locations. |  |
|  |  | Appraisal team | Supports appraisal team leader. |  |
|  |  | Appraisal participants | Learn their role(s) in appraisal activities. |  |

Table 2-18.  Participants for Conduct Opening Meeting.

.  Participants for Conduct Opening Meeting.;

2.2.1 Conduct Opening Meeting, Continued

| Input(s) | Appraisal Plan |
| --- | --- |

| #### Steps | Table 2-19 shows the steps for this process element. |  |  |  |
| --- | --- | --- | --- | --- |
|  |  | Step | Description |  |
|  |  | Invite sponsor comments | The sponsor expresses support for the appraisal and commitment to the resulting process improvement recommendations. The sponsor indicates how the results of the appraisal will be used to accomplish improvement. |  |
|  |  | Introduce FAA-iCMM | The briefing includes an introduction to and description of the FAA-iCMM. |  |
|  |  | Present appraisal process | An overview of the appraisal process is given. Confidentiality rules are explained. |  |
|  |  | Review schedule | The site coordinator reviews the schedule and locations for the week's activities and stresses the necessity of being on time. |  |
|  |  | Invite and answer questions | The sponsor, appraisal team leader, and organizational appraisal representative answer any questions from the appraisal participants. |  |

Table 2-19.  Steps for Conduct Opening Meeting..  Steps for Conduct Opening Meeting.;

| #### Outputs | - Participants ready for appraisal |
| --- | --- |

| #### Typical duration/ effort | Typical calendar duration: 1.5 hrs Typical level of effort: 1.5 hrs for each participant and team member |
| --- | --- |

| #### Notes | Refer to Appraisal Tool Kit, for a sample opening briefing. The appraisal goals and use of results are established in the preparation phase as part of Select Appraisal Scope. |
| --- | --- |

### 2.2.2 Conduct Interviews

| #### Purpose | The purpose of Conduct Interviews is to gather data from appraisal participants, and to understand process implementation issues not resolvable during documentation reviews. |
| --- | --- |

| #### Summary description | The Appraisal Team Leader will determine the type of interview session appropriate for the information needed, either an individual or group interview. The rules of confidentiality should be communicated to all interview participants. Individual interviews will promote, to the maximum extent possible, open discussion. Group interviews, although structured, are to be conducted as open forums for discussion. The group style of interview session provides for appropriate representation to avoid misunderstandings and mistakes. The use of “mini teams” is encouraged, and parallel interviews may be required to complete the activity within the time constraints. The Appraisal Team Leader will designate the leaders for “mini teams”. |
| --- | --- |

| #### Entry criteria | • Exploratory question sets have been scripted. • Interviews have been planned and scheduled. |
| --- | --- |

| #### Exit criteria | • An understanding of each interviewee’s perspective of project level, and organizational processes. • The appraisal team requires no additional perspective, or information, best obtainable through interview sessions. • All documents identified during the interview sessions have been requested. • All process areas within the scope of the appraisal have been addressed by participants with appropriate knowledge of processes and practices. |
| --- | --- |

Continued on next page

2.2.2 Conduct Interviews, Continued

| #### Roles | Table 2-20 lists the principle roles involved in this process element, and a summary of their activities. |  |  |  |
| --- | --- | --- | --- | --- |
|  |  | Role | Summary |  |
|  |  | Appraisal team leader (or appraisal team member if designated) | Leads the interview session, ensuring the correct person (interviewer) is conducting the interview. Ensures that the key exploratory questions are addressed. |  |
|  |  | Organizational appraisal representative or Site coordinator | Ensures attendance of the participants. |  |
|  |  | Appraisal team | Takes notes during interviews. Notes artifacts and documents mentioned during the interview. Asks questions to seek additional information, or clear up ambiguity. |  |
|  |  | Data Manager | Makes a list of artifacts and documents requested by the Appraisal team leader, or other team member. Provides the interviewee, and Organizational appraisal representative or Site coordinator, with a copy subsequent to the session. Keeps track of items requested, received, and returned by the appraisal team. |  |
|  |  | Timekeeper | Ensures compliance with time constraints. |  |
|  |  | Interviewee or Group | Provide the appraisal team with knowledge of process. Discuss practices performed. Provide the appraisal team with samples of the work products, which support process claims. |  |

Table 2-20.  Participants for Conduct Interviews

| #### Inputs | • Exploratory question sets (from Activity 2.1.7 or templates from the Tool Kit) • Session checklists for the facilitator/moderator |
| --- | --- |

Continued on next page

2.2.2 Conduct Interviews, Continued

| #### Steps |  | Table 2-21 shows the steps for this activity. |  |
| --- | --- | --- | --- |
|  | Step |  | Description |
|  | Introduce participants |  | The Appraisal team leader welcomes the individual or group, and explains the purpose of the interview session. The appraisal team, and interviewees introduce themselves. |
|  | Describe technique |  | The rules of confidentiality are reinforced, and the procedure for the structured interview is described to the interviewees. |
|  | Ask and answer questions |  | The interviewer begins with the exploratory questions. All members of the appraisal team should take notes and ask questions based on established rules. Strict adherence to time constraints is of paramount importance. |
|  | Record requests |  | The data manager records any requests of the appraisal team for documentation, or other data. Follow-up is necessary to ensure that the items are received. |
|  | Close Session |  | The ATL draws the dialogue to a close, thanks the participants and reminds them of the confidentiality rules, and data requests made by the appraisal team. A small amount of time should be afforded the interviewee for questions of the appraisal team, or to offer key information that may have been overlooked. |

Table 2-21.  Steps for Conduct Interviews

| #### Outputs | • Interview notes • List of various artifacts requested during the interview sessions |
| --- | --- |

| #### Typical duration/ effort | • Calendar: 1-4 days • Effort: 1 group or 3-5 individual lead interviews 1-5 groups or 8-10 individual practitioner interviews 1-1.5 team hours per individual interview 1.5-2 team hours per group interview |
| --- | --- |

Continued on next page

2.2.2 Conduct Interviews, Continued

| #### Notes | The ATL guides the interviewees through the data collection process. A checklist for this work is in the toolkit, Training Support Materials. The keys to success are building understanding -- the participants feel that what they provide is useful and comprehended by the appraisal team. To that end, it is recommended that the team apply active listening practices (eye contact, head nods, etc.), while ensuring that all of the critical questions are asked. Open-ended questions such as “If you could change anything to improve quality, what would it be?” should be asked when closing the session. |
| --- | --- |

### 2.2.3 Review Documentation

| #### Purpose | The purposes of Review Documentation are to review documentation collected during previous steps in the appraisal process; to identify additional organization or project documentation relevant to the appraisal; and to use such documentation as part of the data gathering aspect of the appraisal. |
| --- | --- |

| #### Summary description | The appraisal team members identify any additional documentation needed by the appraisal team; the team may describe the type of documentation necessary for the appraisal effort. The requested documentation is collected for review. The data manager keeps track of all documentation provided by the organization being appraised. The appraisal team reviews documentation for data/information to support the appraisal process. |
| --- | --- |

| #### Entry Criteria | Completed Appraisal Plan |
| --- | --- |

| #### Exit criteria | No additional documentation is needed.. |
| --- | --- |

2.2.3 Review Documentation, Continued

| #### Roles | Table 2-22 lists the primary roles involved in this process element and a summary of their activity during this process. |  |  |  |
| --- | --- | --- | --- | --- |
|  |  | Role | Summary |  |
|  |  | Appraisal team | Identifies any additional documentation needed. Independently/individually reviews documentation and takes notes/makes observations while engaged in review of documentation. |  |
|  |  | Site coordinator | Assists appraisal team by arranging for space to store documentation and conduct documentation review. Locates and collects documentation needed by the appraisal team |  |
|  |  | Appraisal team leader | Keeps documentation review progressing according to appraisal activities schedule. |  |
|  |  | Data manager | Maintains accountability of documentation for the appraisal team. |  |

Table 2-22.  Participants for Review Documentation

continued on next page

2.2.3 Review Documentation, Continued

| #### Inputs | Relevant project, program, and organization documents. |
| --- | --- |

| #### Steps | Table 2-23 shows the steps for this process element. |  |  |  |
| --- | --- | --- | --- | --- |
|  |  | Step | Description |  |
|  |  | Review documentation | The appraisal team reviews documentation already collected and takes notes/makes observations as appropriate. |  |
|  |  | Identify additional documentation. | Based on data gathered during individual interviews, group sessions, or documentation review, appraisal team identifies necessary supplemental documentation. |  |
|  |  | Collect and manage documentation | Documentation is located, collected, logged and tracked. |  |

Table 2-23.  Steps for Review Documentation

| #### Output(s) | Notes and observations from reviewed documentation. |
| --- | --- |

| #### Typical duration/ effort | Calendar: 1-3 days Effort: 4-8 team hours |
| --- | --- |

continued on next page

2.2.3 Review Documentation, Continued

| #### Notes | The Review Documentation steps may be repeated because additional documentation may be identified by appraisal team members during a review step. Documentation review could lead to the development of exploratory questions - prior to interviews. A team may request and use documentation generated for or by a process area to demonstrate a capability level. |
| --- | --- |

### 2.2.4  Consolidate Data

| #### Purpose | The purpose of Consolidate Data is to consolidate the notes taken during the individual interviews, group interviews, and the documentation reviews. |
| --- | --- |

| #### Summary description | Consolidate Data involves consolidating notes into observations to reflect the information gained in the individual interviews, group interviews, and document reviews. This phase should be performed multiple times, typically at the conclusion of each data collection session. It also allows the members of the appraisal team to verify their understanding of the information obtained with the other team members. Finally, this data consolidation step allows the team to strategize any needed changes in the data gathering events. |
| --- | --- |

| #### Entry criteria | - At least one interview session has concluded. |
| --- | --- |

| #### Exit criteria | - Team members agree that sufficient coverage has been obtained. |
| --- | --- |

| #### Roles | - Table 2-24 lists the roles involved in this activity. |  |
| --- | --- | --- |
|  | - Role | - Summary |
|  | - Appraisal Team Leader | - Provides guidance and model expertise for the team's deliberations. |
|  | - Appraisal team | - Discusses any issues; formulates observations; ensures that they meet the consolidation requirements of accuracy, validity, and sufficiency; and approves observations by consensus. |

- Table 2-24.  Participants for Consolidate Data..  Participants for Consolidate Data from SE Leads.;

| #### Inputs | - Notes from interview sessions - Observations from document review. |
| --- | --- |

- continued on next page

- 2.2.4  Consolidate data, continued

- Steps			Table 2-25 shows the steps for this activity.

| - Step | - Description |
| --- | --- |
| - Review notes | - Each team member privately reviews his/her notes from the data collection session. |
| - Record observation | - Each team member creates observations from the notes. Each observation should include: a link to the FAA-iCMM PA/BP/GP if applicable; indication that it is a strength, weakness, or alternative practice; session(s) observation was collected; and identification of the team member recording the observation. |
| - Identify missing information | - As missing information is identified, the need is documented and the appraisal strategy is modified as required. |
| - Check for accuracy | - Team members will ensure that the observation is accurate. The appraisal team as a whole will then review the proposed observation. Accuracy includes: - Worded correctly (e.g., clear, does not use absolutes, expressed in site terms, and non-attributable) - Based on information provided and documented in notes - Relevant by determining that it can be mapped to the FAA-iCMM or otherwise has a significant impact on the organization’s process capability - Significant by determining that it can be classified as evidence of strength, weakness, or acceptable alternative practices - Not redundant with other observations |

    - Consolidate data, continued

| - Step | - Description |
| --- | --- |
| - Check for validity | - The appraisal team will ensure that the observation is valid. Validity includes: - Accurate using the criteria described above - Corroborated - - Based on data from at least two independent sources, e.g., two separate people or a person and a document - Based on data obtained during at least two different data gathering sessions - Strengths and alternative practices confirmed by at least one source that indicate actual practice - Consistent with other validated observations (does not include weaknesses that conflict with evidence of strengths or acceptable alternatives) |
| - Check for sufficiency | - The appraisal team will ensure that the set of observations for a goal is sufficient. Sufficiency indicates that data was collected during the assessment to cover the appraisal scope: - the organizational scope of the appraisal - the full life cycle within scope of the appraisal - the FAA-iCMM components within scope of the appraisal - observations cover each BP - observations cover each GP Sufficiency also requires that a document indicating the work is performed has been examined for each goal within the scope of the appraisal. |

- Table 2-25.  Steps for Consolidate Data.  Steps for Consolidate Data from SE Leads.;

    - Consolidate data, continued

| #### Outputs | - Summarized, valid, accurate, and corroborated observations recorded by process area. |
| --- | --- |

| #### Typical duration/ effort | Typical duration: Four to eight hours total during the data gathering (4 days) Typical level of effort: 8 or more team hours |
| --- | --- |

| #### Notes | If sufficiency is not attainable in a reasonable amount of time, this goal will be “not rated” (see 2.2.7). This is detailed work and tends to be exhausting. |
| --- | --- |

### 2.2.5 Develop Draft Findings

| #### Purpose | The purpose of Develop Draft Findings is to develop findings for each process area investigated in the appraisal. |
| --- | --- |

| #### Summary description | Develop Draft Findings involves analyzing the consolidated observations and synthesizing them into a manageable set for incorporation into the final briefing. |
| --- | --- |

| #### Entry criteria | - Data has been consolidated - Team consensus that sufficient coverage has been obtained |
| --- | --- |

| #### Exit criteria | - • Consensus is obtained on draft findings. - • Draft findings briefing is developed. |
| --- | --- |

| #### Roles | - Table 2-26 lists the roles involved in this activity. |  |
| --- | --- | --- |
|  | - Role | - Summary |
|  | - Appraisal team leader | - Provides expertise on the FAA-iCMM and the appraisal method and guides the team in forming consensus. |
|  | - Appraisal team | - Develops draft findings - Achieves or forms consensus |

- Table 2-26.  Participants for Develop Draft Findings..  Participants for Develop Draft Findings.;

- continued on next page

- 2.2.5 Develop Draft Findings, continued

| #### Inputs | - Consolidated data - Template for findings |
| --- | --- |

| #### Steps | - Table 2-27 shows the steps for this activity. |  |
| --- | --- | --- |
|  | - Step | - Description |
|  | - Develop draft findings | - Review the observations. Identify those major issues for each PA that need to be presented to the appraised organization. There are sometimes local issues that must be addressed if the appraisal is to have credibility with the participants. These may be identified as non-FAA-iCMM or cultural findings. Craft well-worded findings. Mini-teams typically develop these draft findings. |
|  | - Prioritize findings | - Prioritization is based on business goals, if available, or on the team's consensus on the major barriers to improvement in the organization. |
|  | - Form consensus | - Each finding is presented to the team for final edit and approval. The team must agree to support each finding. - This step continues until consensus is achieved. If consensus is not achieved the finding should not be used. |
|  | - Prepare briefing charts | - The findings are placed on briefing charts for presentation. See the Toolkit for a sample of the findings presentation slides. |

- Table 2-27.  Steps for Develop Draft Findings.  Steps for Develop Draft Findings, continued;

| #### Outputs | - Draft findings |
| --- | --- |

| #### Typical duration/ effort | - Typical duration: Four to eight hours - Typical level of effort: 4 - 8 team hours |
| --- | --- |

- continued on next page

- 2.2.5 Develop Draft Findings, continued

| #### Notes | - A finding is: - Worded correctly (clear, does not use absolutes, expressed in site terms, and non-attributable to person or project) - A group of observations, either strengths or weaknesses. If team members leave the appraisal without full commitment to all of the findings, the other participants will sense the lack of consensus and interpret it as a weakness in the findings. |
| --- | --- |

### 2.2.6  Present Draft Findings

| #### Purpose | The purpose of Present Draft Findings is to validate that the synthesized findings represent the information provided during data gathering. This session is important in establishing the credibility of the appraisal with the participants and for providing momentum toward change. |
| --- | --- |

| #### Summary description | Present Draft Findings involves presenting the synthesized findings to the managers as a group, and to all the practitioners as a group. This provides the opportunity for participants to provide feedback on the validity of the information. Generally all managers and strong opinion leaders are grouped in one group, with the other participants in the other group. The team later revises findings, if appropriate. |
| --- | --- |

| #### Entry Criteria | - Draft findings slides prepared |
| --- | --- |

| #### Exit Criteria | - Presentation of draft findings complete. - Participant comments recorded and findings are updated. |
| --- | --- |

| #### Roles | - Table 2-28 lists the roles involved in this activity. |  |
| --- | --- | --- |
|  | - Role | - Summary |
|  | - Appraisal team leader or OAR | - Presents the draft findings. Solicits comments from participants. Facilitates the feedback portion of the meeting. |
|  | - Appraisal team | - Observes reactions of participants to findings, and takes notes on the feedback. Modify findings as needed and come to consensus on the findings. |
|  | - Appraisal participants | - Listen to findings presentation; provide feedback on whether the appraisal team captured what is happening in the organization. Offer improvements. |

- Table 2-28.  Participants for Present Draft Findings..  Participants for Present Draft Findings.;

| #### Inputs | - Draft findings slides (from activity 2.2.5) |
| --- | --- |

### 2.2.6  Present Draft Findings, continued

| #### Steps | - Table 2-29 shows the steps for this activity. |  |
| --- | --- | --- |
|  | - Step | - Description |
|  | - Describe purpose of session | - Re-emphasize that the goal of the appraisal is to capture the "state of the practice" in the appraised entity; this session allows the appraisal team to validate that they have accurately captured the viewpoint of the participants. No copy of the briefing should be passed out at this time. No note taking is allowed by the participants. |
|  | - Present findings | - Present the findings portion of the briefing. During this briefing, observe the reactions to the findings. |
|  | - Validate findings | - After the run-through of the findings, solicit feedback from the practitioners, e.g., "Is this what you told us and is this worded in a way to get positive action from management?" Lead the discussion. When changes are proposed, no commitment to change is made, but the comment is simply recorded. |
|  | - Adjourn meeting | - Remind participants of the time for the final findings briefing and emphasize that this is an opportunity to interact with the management who sponsored the appraisal. |
|  | - Review suggested changes to findings | - Not all requested changes will be accepted, particularly, ones that do not add to the critical issues of the appraisal. The information received in the Draft Findings session will be treated as data obtained from another data collection session. The team must come to consensus on the changes before they are made. |

- Table 2-29.  Steps for Present Draft Findings.  Steps for Present Draft Findings, continued;

| #### Outputs | - Notes by team - Revised findings |
| --- | --- |

### 2.2.6  Present Draft Findings, continued

| #### Typical duration/ effort | Typical duration: One hour for each presentation; two hours to update findings. Typical level of effort: Four team hours plus 1 participants’ hour |
| --- | --- |

| #### Notes | Feedback helps to validate and gather consensus of the need for change. Ask the participants to keep findings to themselves until after the findings briefing. This gives sponsors a chance to respond to the findings. |
| --- | --- |

### 2.2.7  Develop Ratings

| #### Purpose | The purpose of Develop Ratings is to develop the process capability profile and to determine a maturity rating. |
| --- | --- |

| #### Summary description | Develop Ratings involves the appraisal team coming to consensus on the process capability profile and the maturity rating. The capability rating of each PA is determined by coming to consensus on the extent to which the appraised organization meets the goals of each process area and capability level within scope of the assessment. These capability ratings together constitute the process capability profile. The maturity rating can then be derived from the profile. |
| --- | --- |

| #### Entry criteria | - Updated findings |
| --- | --- |

| #### Exit criteria | - Process capability profile is finalized. - Maturity rating is finalized. |
| --- | --- |

| #### Roles | - Table 2-30 lists the roles involved in this activity. |  |  |  |
| --- | --- | --- | --- | --- |
|  |  | - Role | - Summary |  |
|  |  | - Appraisal team | - Develops and comes to consensus on the process capability profile and maturity rating. |  |

- Table 2-30.  Participants for Develop Ratings..  Participants for Adjust Draft Findings.;

| #### Inputs | - Observations - Updated findings |
| --- | --- |

### Develop Ratings, continued

- Steps			Table 2-31 shows the steps for this activity.

| - Step | - Description |
| --- | --- |
| - Determine classification of PA goal | - Review each goal for each PA and classify that goal as: - Not Rated - The appraisal findings do not sufficiently cover the goal (as defined in section 2.2.4) or the goal falls outside the scope of the appraisal. - Not Applicable - The FAA-iCMM goal is not applicable to the organization’s environment. - Satisfied - The base practices associated with the PA goal are performed as defined in the FAA-iCMM or with adequate alternative practices. There must be no significant weaknesses. - Unsatisfied - There are significant weaknesses in the performance of the base practices associated with the goal, and no adequate alternatives in place. |
| - Determine classification of PA implementation | - Review the PA goal classifications for each PA and classify that PA as: - Not Rated – At least one goal for the PA is classified as Not Rated. - Not Applicable – All goals for the PA are classified as Not Applicable. - Implemented – All goals are classified as Satisfied or at least one goal is classified as Satisfied with all other goals classified as Not Applicable. - Not implemented – All goals are rated and at least one goal is classified as Unsatisfied. |

### Develop Ratings, continued

| - Determine classification of capability level goals for PA | - For each implemented PA, review each capability level goal and classify that goal as: - Not Rated - The appraisal findings do not sufficiently cover the goal (as defined in section 2.2.5) or the goal falls outside the scope of the appraisal. - Satisfied - The generic practices associated with that capability level goal are performed as defined in the FAA-iCMM or with adequate alternative practices. There must be no significant weaknesses. - Unsatisfied - There are significant weaknesses in the performance of the generic practices associated with that capability level goal, and no adequate alternatives in place. |
| --- | --- |
| - Determine institutionalization classification (capability level) for PA | - Review each PA’s implementation classification and its capability level goal classification and classify the PA as: - Not Rated - The PA implementation classification is Not Rated. No capability level is assigned; the PA is classified as Not Rated (NR). - Not Applicable - The PA implementation classification is Not Applicable. No capability level is assigned; the PA is classified as Not Applicable (NA) - Institutionalized at level X - The PA implementation classification is Implemented and the PA capability level goals up to and including level X are satisfied. If the PA is Implemented but the Level 2 capability level goal is Unsatisfied or Not Rated, then the PA is determined to be Implemented (Level 1). If the PA is Not Implemented then no capability level is assigned; the PA is classified as Not Implemented (NI). |

### Develop Ratings, continued

| - Check for consistency | - The capability rating is compared with the strengths and weaknesses of each PA (including global strengths and weaknesses) to insure consistency. |
| --- | --- |
| - Develop Process Capability Profile | - The process capability profile is determined by charting each PA capability level (1-5) or classification. |
| - Determine Maturity Rating | - All PAs associated with a maturity level and all PAs assigned a lower maturity level must be Institutionalized at that level (or higher), or classified as “Not Applicable.” This will result in a single Maturity Rating for the appraised entity (1-5). |

- Table 2-31.  Steps for Develop Ratings

| #### Outputs | - Organization profile and project profile, as appropriate - Maturity level rating |
| --- | --- |

| #### Typical duration/ effort | - Typical duration: Two to four hours - Typical level of effort: 2-4 team hours |
| --- | --- |

### 2.2.7  Develop Ratings, continued

| #### Notes | - Note that the structure of the FAA-iCMM is such that base practices are mapped to PA Implementation Goals, and generic practices are mapped to Capability Level (Institutionalization) Goals. The FAA-iCMM Appraisal Method develops ratings consistently regarding both aspects of the model. - Develop Ratings is performed simultaneously with the last step of Present Draft Findings and the first step of Develop Final Briefing. A typical scenario would be to develop final findings, ratings, summaries, recommendations, and come to consensus in an iterative fashion. - The term “rated” is used to define a PA that does not have the classification of “Not Rated”. - A PA must be found to be Implemented if the findings indicate that the organization implements all related practices or acceptable alternatives to related practices. - An implemented PA must be found to be Institutionalized at a given level if the findings indicate that the organization implements all related generic practices or acceptable alternatives to related generic practices. - A PA can only be Implemented if the findings identify related strengths. - A PA cannot be Institutionalized at a specific level unless the findings indicate that the process is institutionalized and has been in place for a satisfactory period of time. - A PA can only be Not Implemented if the findings identify related weaknesses. |
| --- | --- |

### 2.2.8  Develop Final Briefing

| #### Purpose | The purpose of Develop Final Briefing is to prepare the final briefing to the sponsor and participants. |
| --- | --- |

| #### Summary description | Develop Final Briefing involves the appraisal team coming to consensus on the final briefing. |
| --- | --- |

| #### Roles | Table 2-32 lists the roles involved in this activity. |  |
| --- | --- | --- |
|  | Role | Summary |
|  | Appraisal team | Makes changes to the briefing if needed and comes to consensus on them. Provides global, cultural, and other non-FAA-iCMM finding slides as well as the beginning and closing part of the briefing. Prepares slides and enough copies of the final briefing for the sponsor and the appraisal team, plus a few extras in case the sponsor wants extras for his/her own distribution. |

Table 2-32.  Participants for Develop Final Briefing

| #### Inputs | - Process capability profile (from activity 2.2.7) - Maturity level rating (from activity 2.2.7) - Validated, updated findings (from activity 2.2.6) - Template for presentation (Toolkit) - Checklist for the activity |
| --- | --- |

### 2.2.8  Develop Final Briefing, continued

- Steps			Table 2-33 shows the steps for this activity.

| - Step | - Description |
| --- | --- |
| - Prepare final briefing | - The appraisal team develops, reviews, modifies, and comes to consensus on all parts of the briefing. This includes: - Opening and closing - PA findings and ratings - Next steps - Findings found across many PAs that are identified as “global” findings. - Non-FAA-iCMM findings regarding the culture that are identified as “cultural” findings. - Other non-FAA-iCMM findings - PA “Summaries”, and “Recommended Actions.” The recommended actions should address weaknesses. |
| - Ensure consistency of final briefing | - Ensure that there is no conflict and that the final briefing is consistent. |
| - Produce final briefing | - Create the final charts, and copies of the briefing. |

- Table 2-33.  Steps for Develop Final Briefing..

| #### Outputs | - Final briefing is prepared for delivery to participants. |
| --- | --- |

| #### Typical duration/ effort | Typical duration: 1-4 hours Typical level of effort: 1-4 team hours |
| --- | --- |

| #### Notes | Be sure the presenter(s) are comfortable delivering the briefing and that the whole team supports the results. |
| --- | --- |

### 2.2.9 Brief Sponsor

| #### Purpose | The purposes of Brief Sponsor are to provide the sponsor with an opportunity to see results and findings and to ask questions privately, to obtain or provide feedback on the appraisal process, and to discuss next steps in more detail. |
| --- | --- |

| #### Summary description | Brief Sponsor involves the appraisal team members and sponsor having an open discussion on the results of the appraisal, the appraisal process, and/or the next steps, as appropriate. All confidentiality rules are still in effect for this meeting. No results or findings are changed as a result of this meeting with the sponsor, but the sponsor is the first to see them so that the final briefing session is not a surprise. |
| --- | --- |

| #### Entry Criteria | Appraisal findings completed and process capability profile developed. |
| --- | --- |

| #### Exit criteria | • Sponsor is briefed on appraisal results. |
| --- | --- |

| #### Roles | Table 2-34 lists the primary roles involved in this process element and a summary of their activity during this process. |  |  |  |
| --- | --- | --- | --- | --- |
|  |  | Role | Summary |  |
|  |  | Appraisal team leader or organization appraisal representative | Asks sponsor if any clarification or other information is needed, suggests follow-on activities or assignments. Reaffirms confidentiality of participants responses and comments. |  |
|  |  | Appraisal team | Answer sponsor's questions, as appropriate. |  |
|  |  | Sponsor | Asks any questions not appropriate for a general audience; makes follow-up assignments. |  |

Table 2-34.  Participants for Brief Sponsor..  Participants for Brief Sponsor.;

### 2.2.9 Brief Sponsor, Continued

| #### Input(s) | Final briefing. |
| --- | --- |

| #### Steps | Table 2-35 shows the steps for this process element. |  |  |  |
| --- | --- | --- | --- | --- |
|  |  | Step | Description |  |
|  |  | Brief sponsor | Present results and findings to sponsor and review highlights of appraisal activities. Thank sponsor for providing appraisal opportunity. Reaffirm confidentiality. Reassert need for sponsor to attend final briefing and to speak to appraisal participants. |  |
|  |  | Ask for feedback | Often the sponsor has questions of clarification that he/she prefers not to ask in a large group; even if there are no specific questions, this is a good time to gauge the sponsor's reaction – sometimes the results are right in line with the sponsor's prior thinking, sometimes they are a surprise. |  |
|  |  | Record feedback | Any feedback from the sponsor on the appraisal process should be noted on a form and included in the lessons learned that are returned to the FAA-iCMM organization maintenance site. |  |
|  |  | Discuss next steps | At this point the assignments for follow-on work should be finalized. The briefer may provide some advice on how long the follow-up activities will be expected to take and the level of commitment required to finish the report and start to develop an improvement plan. Remind sponsor to take responsibility for improvement and to address follow-on actions |  |

Table 2-35.  Steps for Brief Sponsor..  Steps for Brief Sponsor.;

### 2.2.9 Brief Sponsor, Continued

| #### Output(s) | • Affirmation of appraisal results by sponsor. |
| --- | --- |

| #### Typical duration/ effort | Thirty minutes to one hour for sponsor and each appraisal team member. |
| --- | --- |

| #### Notes | This is an optional step, but is frequently used as a way to ensure sponsor follow-through and assignment of actions. It also provides the sponsor with an opportunity to see results and findings (privately) and to get a better understanding of the findings so that he/she may be more comfortable discussing the appraisal results and findings in front of or among the appraisal participants at the final briefing. Attendance at a sponsor briefing may be limited, for example to the ATL and OAR, based on sponsor’s preference. |
| --- | --- |

### 2.2.10 Present Final Briefing

| #### Purpose | The purposes of Present Final Briefing are to present the appraisal results and findings to the organization’s appraisal participants; to provide the sponsor with an opportunity to reaffirm support for the appraisal process and the associated results and findings; and to discuss follow-on activities which address the results and findings. (e.g., catalyst for process improvement effort). |
| --- | --- |

| #### Summary description | Present Final Briefing involves presenting the results of the appraisal to the appraisal participants and to the sponsor via a briefing that synthesizes the results and findings in a non-attributable form. Note that the sponsor may have already been briefed in private on the appraisal results and findings, but now has an opportunity to publicly reaffirm his/her support for the efforts of the appraisal team and to thank his/her organization’s participants for their effort and support. |
| --- | --- |

| #### Entry Criteria | Complete set of final briefing charts/slides and other materials. |
| --- | --- |

| #### Exit criteria | • Final briefing presentation completed. • Participant questions answered, or recorded as actions. |
| --- | --- |

### 2.2.10 Present Final Briefing, continued

| #### Roles | Table 2-36 lists the primary roles involved in this process element and a summary of their activity during this process. |  |  |  |
| --- | --- | --- | --- | --- |
|  |  | Role | Summary |  |
|  |  | Appraisal team leader or organization appraisal representative | Presents the final briefing. |  |
|  |  | Appraisal team | Notes feedback from participants and sponsor. |  |
|  |  | Sponsor | Receives appraisal results and findings from team; reaffirms support for the effort; discusses actions to be taken based on appraisal results. |  |
|  |  | Appraisal participants | Listen to appraisal results and provide recommendations to sponsor where appropriate. |  |

Table 2-36.  Participants for Present Final Briefing..  Participants for Present Final Briefing.;

| #### Input(s) | Appraisal findings and process capability profile |
| --- | --- |

2.2.10  Present Final Briefing, Continued

| #### Steps |  |  | Table 2-37 shows the steps for this process element. |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Step | Description |  |
|  |  |  |  | Present final briefing | The presenter goes through the entire briefing, including process capability profile and next steps; presenter asks for questions to be held until the end. Team takes notes on any feedback. |  |
|  |  |  |  | Conduct open discussion | Usually at the end of the briefing, the sponsor gives a "thank you" message, provides initial reaction, and then opens with his/her own questions or opens the discussion to the floor. |  |
|  |  |  |  | Thank sponsor and participants | Acknowledge the support personnel and all those who helped the appraisal succeed. |  |

Table 2-37.  Steps for Present Final Briefing..  Steps for Present Final Briefing.;

| #### Output(s) | - Action items from briefing presentation - Notes on participant reaction/feedback |
| --- | --- |

| #### Typical duration/ effort | One to two hours duration for each appraisal team member and each appraisal participant. |
| --- | --- |

| #### Notes | Before the actual briefing the sponsor should be coached on his/her participation in the meeting - i.e., the sponsor should be reminded that his/her reaction will have an impact on the reaction to follow-on actions. |
| --- | --- |

### 2.2.11 Conduct Wrap-Up

| #### Purpose | The purposes of Conduct Wrap-Up are to obtain feedback from the appraisal team on the appraisal process; to provide an opportunity for consulting with the appraisal team leader and organization appraisal representative on moving forward with the results to ensure that appraisal materials are properly accounted for; to return all documentation provided by the (appraised) organization to its proper location or custodian; and to begin the process of preparing a list of “what worked” and “what did not work.” |
| --- | --- |

| #### Summary description | Conduct Wrap-Up involves obtaining information about what worked and what did not work from the appraisal team members for feeding back to the process improvement organization. It also involves discussing and resolving findings and assignments from the recommendation(s) report. It requires returning all documentation and/or other materials borrowed for the appraisal to the appropriate accountable individuals, and making certain that the appraisal rooms/locations are restored to their pre-appraisal condition(s). Finally the development of a lessons learned report is begun. |
| --- | --- |

| #### Entry Criteria | Appraisal completed and briefing presented |
| --- | --- |

| #### Exit criteria | - Appraisal lessons learned are recorded. - Assignments are verified. - Actual schedule and resource utilization are recorded - Documentation and materiel returned. - Appraisal rooms/locations cleaned up. |
| --- | --- |

### Conduct Wrap-Up,  Continued

| #### Roles | Table 2-38 lists the primary roles involved in this process element and a summary of their activity during this process. |  |  |  |
| --- | --- | --- | --- | --- |
|  |  | Role | Summary |  |
|  |  | Appraisal team leader/ organization appraisal representative | Facilitates gathering data on what worked and did not work during the appraisal. |  |
|  |  | Appraisal team members | Provide input into what worked and what didn't work. Clean up appraisal locations. |  |
|  |  | Data manager | Return documentation and material. |  |

Table 2-38.  Participants for Conduct Wrap-Up..  Participants for Conduct Wrap-Up.;

| #### Input(s) | Action items from final briefing. |
| --- | --- |

continued on next page

### 2.2.11  Conduct Wrap-Up,  Continued

| #### Steps | Table 2-39 shows the steps for this process element. |  |  |  |
| --- | --- | --- | --- | --- |
|  |  | Step | Description |  |
|  |  | Collect lessons learned | Appraisal team notes “lessons learned” - i.e., “what worked” and “what did not work”- and planned Vs actual schedule and resource utilization |  |
|  |  | Review comments | Note comments from appraisal participants that arose during final briefing. |  |
|  |  | Answer last-minute questions | Often appraisal team members have questions about improvement plans, etc., that the ATL can spend some time answering and/or providing references for. |  |
|  |  | Return material and clean up. | Return borrowed documentation to appropriate custodians and return other materials. Clean up rooms and restore to original condition. |  |

Table 2-39.  Steps for Conduct Wrap-Up..  Steps for Conduct Wrap-Up.;

| #### Output(s) | - Schedule for completion of appraisal report. |
| --- | --- |

| #### Typical duration/ effort | Duration: 2-4 hours Effort: 2-4 hours for each appraisal team member. |
| --- | --- |

| #### Notes | There may be resistance to conducting a wrap-up session ; therefore, this step must occur immediately after the final briefing. |
| --- | --- |

### 2.3 Report Results

| #### Purpose | The purpose of the Report Results phase is to prepare the appraisal report, document lessons learned in the appraisal, and manage appraisal records. |
| --- | --- |

| #### Summary description | The Record Results phase contains 2 activities as depicted below. |
| --- | --- |

| #### Diagram |  |
| --- | --- |

Prepare and Deliver Appraisal Report

- Review final briefing

- Plan the preparation of the report

- Write the report

- Review/revise the report

- Distribute/deliver the report

|

Manage Records

- Gather materials

- Decide disposition

- Transfer materials to be kept

- Destroy unwanted materials

### 2.3.1 Prepare and Deliver Appraisal Report

| #### Purpose | The purpose of Prepare and Deliver Appraisal Report is to provide details or explanations beyond what was contained in the final briefing. |
| --- | --- |

| #### Summary description | The report provides the organization with documentation of the appraisal. |
| --- | --- |

| #### Entry criteria | - On site phase completed |
| --- | --- |

| #### Exit criteria | - Report delivered and accepted or approved by sponsor |
| --- | --- |

| #### Roles | Table 2-40 lists the primary roles involved in this activity and a summary of responsibilities. |  |  |  |
| --- | --- | --- | --- | --- |
|  |  | Role | Summary |  |
|  |  | Organizational appraisal representative or appraisal team leader | Coordinates preparation of report. |  |
|  |  | Appraisal team | Individual team members perform writing assignments and act as peer reviewers for the entire appraisal report. |  |

Table 2-40.  Participants for Prepare and Deliver Appraisal Report..  Participants for Report Lessons Learned..  Participants for Report Lessons Learned.;

| #### Inputs | - Final briefing - Notes |
| --- | --- |

### 2.3.1 Prepare and Deliver Appraisal Report, continued

| #### Steps | Table 2-41 shows the steps for this activity. |  |  |  |
| --- | --- | --- | --- | --- |
|  |  | Step | Summary |  |
|  |  | Review final briefing | Review the final briefing |  |
|  |  | Plan the preparation of the report | Determine what needs to be provided in the final report, and who should do what, by when. |  |
|  |  | Write the report | Write the report |  |
|  |  | Review/revise the report | Peer review the report and revise as required. |  |
|  |  | Distribute/deliver the report | Distribute the report to its intended recipients. |  |

Table 2-41.  Participants for Prepare and Deliver Appraisal Report..  Participants for Report Lessons Learned..  Participants for Report Lessons Learned.;

| #### Outputs | Appraisal report |
| --- | --- |

| #### Typical duration/ effort | Typical duration: 1-4 weeks Typical level of effort: 1-5 team days |
| --- | --- |

| #### Notes | In the simplest case, the appraisal report may be a copy of the final briefing. Appraisal notes may be used in writing the report and during peer review to assist in developing recommendations and in verification of accuracy of the appraisal report. The following data, at a minimum, shall be provided to the sponsor: - Appraisal scope - Appraisal selections (site, projects, participants, team members) - Findings - Ratings |
| --- | --- |

### 2.3.2 Manage Records

| #### Purpose | The purpose of Manage Records is to verify that all records of the appraisal, both intermediate and final, are disposed of or handed off in accordance with agreed-upon appraisal ground rules. |
| --- | --- |

| #### Summary description | Manage Records involves reviewing all the gathered appraisal materials and ensuring their proper disposition. Most intermediate notes and work products are appropriately destroyed once the appraisal report is complete. Notes may be kept until then to provide context for recommendations and to verify the accuracy of the report. |
| --- | --- |

| #### Entry criteria | - Appraisal report completed |
| --- | --- |

| #### Exit criteria | - Records being kept are secured - Records not needed are destroyed |
| --- | --- |

| #### Roles | Table 2-42 lists the primary roles involved in this activity and a summary of their responsibilities. |  |  |  |
| --- | --- | --- | --- | --- |
|  |  | Role | Summary |  |
|  |  | Appraisal team | Gathers notes and other records and appropriately disposes of them. |  |
|  |  | Organization appraisal representative | Ensures all records are properly managed. |  |
|  |  | Process Improvement Organization | Maintains a library of FAA-iCMM appraisal reports |  |

Table 2-42.  Participants for Manage Records..  Participants for Report Lessons Learned.;

| #### Inputs | - All appraisal materials - Appraisal ground rules |
| --- | --- |

### 2.3.2 Manage Records, continued

| #### Steps | Table 2-43 shows the steps for this activity. |
| --- | --- |

| Step | Summary |
| --- | --- |
| Gather materials | Gather all appraisal materials |
| Decide disposition | Decide disposition of materials according to groundrules |
| Transfer material to be kept | Transfer appraisal report and any other materials to be managed to the process improvement organization and to the SEI as appropriate |
| Destroy unwanted materials | Destroy materials that are not to be managed |

Table 2-43.  Steps for Manage Records..  Participants for Report Lessons Learned..  Participants for Report Lessons Learned.;

| #### Outputs | - Process asset repository updated with material to be saved |
| --- | --- |

| #### Typical duration/ effort | Typical duration: One to two hours Typical level of effort: 1-2 person hours |
| --- | --- |

| #### Notes | For the records to be kept, the security provided should be equivalent to that for personnel actions. It is important that the integrity of the team be maintained; violation of the stated confidentiality rules, even after the fact, can damage future appraisal activities. |
| --- | --- |