## Sheet1
Simulator Development Timeline
| Task ID | Oct | [6 empty] | Nov | [7 empty] | Dec |  |  | Jan |  |  | Feb | Mar | Apr
Control Manager | 1. Determine how hardware layout will look and function
5-8
2. Define interface with Track Manager
5-19
3. Define rules to avoid conflicting requests from UI and collisions
|  | (1) | [5 empty] | 8-25
4. Define command set with UI team
|  | (1) |  |  | 8-11
5. Design protocol to communicate with UI
|  |  | (4) |  |  |  | 12-15
6. Design and implement code for sub-components
[6 empty] | (2,3,5) | [8 empty] | 26-24
7. Integrate and test Control Manager sub-components
[13 empty] | (6) |  |  |  | 25-30
Simulator Engine | 8. Develop Simulator engine
8-7
9. Develop Short Circuit block
8-15
10. Develop interface to Command Interpreter
16-24
11. Integration of Simulation Engine sub-components
[11 empty] | (8,9,10) | [5 empty] | 25-30
Track Manager | 12. Link list design, coding and testing for track layout
5-19
13. Develop and test algorithm for track info retrieval
[5 empty] | (12) |  |  |  |  | 20-4
14. Implement algorithm for mutual exclusion of multiple users
[8 empty] | (13) | [5 empty] | 5-20
15. Algorithm for matching user requests with actual track conditions
[12 empty] | (14) |  |  |  | 21-24
16. Integrated testing of Track Manager sub-components
[14 empty] | (15) |  |  | 25-30
Dependencies are in ()
Dates are displayed in ranges start-finish
Simulator Development Timeline
Integration & Documentation | Task ID | Oct | [6 empty] | Nov | [7 empty] | Dec |  |  | Jan |  |  | Feb | Mar | Apr
17. Integrate Simulator components
[13 empty] | (7,11,16) |  |  |  |  | 1-7
18. Extensive Simulator testing
[17 empty] | (17) | [6 empty] | 8-28
19. Write Interim report
25-31
20. UI and Command Interpreter integration and testing
[19 empty] | (17) |  |  | 1-15
21. Total software and hardware integration and testing
[21 empty] | (20) |  |  | 16-28
22. Write Final Report
1-31
Dependencies are in ()
Dates are displayed in ranges start-finish