## labourcalcu-bag
Summary Of Quantity And Labour Calculaion
Project : Bagarkot-Bhageswar Green Road
V.D.C : Bagarkot
SN | Description of Works | Unit | Qty. | Labour Per Unit |  | Total MD
|  |  |  | Unskilled | Skilled | Unskilled | Skilled
1 | Site Clearance Clearing and grubbing including the cutting of trees having girth of less than 30 cm when measured at 1 m above the ground | m2 | 7743.24 | 0.04 | 0 | 309.7296 | 0
2 | Cutting of trees: having girth of above 30 cm when measued at 1m above the ground including the removal along the lead route for trees of size: |  |  |  |  | 0 | 0
| i) 30-60 cm girth | No. | 82 | 0.3 | 0 | 24.6 | 0
| ii)60-90 cm girth | No. | 37 | 0.4 | 0 | 14.8 | 0
| iii) 90-180 cm girth | No. | 23 | 1.5 | 0 | 34.5 | 0
| iv) 180-270 cm girth | No. | 38 | 3 | 0 | 114 | 0
| v) 270-450 cm girth | No. | 0 | 10 | 0 | 0 | 0
3 | Excavation of roadway and drain Including disposal of material up to a lead of 50 m along the lead route
| i) Ordinary soil | m3 | 6500.4193 | 0.5 | 0 | 3250.2097 | 0
| ii)Hard soil | m3 | 7190.357 | 0.6 | 0 | 4314.2142 | 0
| iii) Ordinary rock | m3 | 4905.8103 | 2 | 0 | 9811.6206 | 0
| iv)Medium rock | m3 | 3275.6141 | 4 | 0 | 13102.4563 | 0
| v)Hard rock requirng chiseling | m3 | 0 | 17 | 0 | 0 | 0
4 | Construction of Roadway embankments and miscellaneous backfilling areas with approved material | m3 | 6370.2437 | 0.25 | 0 | 1592.5609 | 0
5 | Earth filling with extra lead
A. Soil Transportation
| I) At 50m extra lead | m3 | 78.91 | 0.5 | 0 | 39.455 | 0
| iI) At 100m extra lead | m3 | 47.346 | 1 | 0 | 47.346 | 0
| iiI) At 150m extra lead | m3 | 23.673 | 1.5 | 0 | 35.5095 | 0
| iv) At 200m extra lead | m3 | 7.891 | 2 | 0 | 15.782 | 0
6 | Excavation in foundation for structures Including disposal of material up to a lead of 50 m.
| i) Ordinary soil | m3 | 95.1182 | 1 | 0 | 95.1182 | 0
| ii)Hard soil | m3 | 142.6062 | 2 | 0 | 285.2125 | 0
| iii) Ordinary rock | m3 | 394.5438 | 4 | 0 | 1578.1752 | 0
| iv)Medium rock | m3 | 284.3702 | 8 | 0 | 2274.962 | 0
| v)Hard rock requirng chiseling | m3 | 0 | 30 | 0 | 0 | 0
7 | Dry stone masonary retaining wall work .(including scafolding) | m3 | 1617.74 | 1.5 | 0.5 | 2426.61 | 808.87
8 | Gabion retaining wall Work a).Fabrication of gabion boxes including rolling, cutting, assembling of wire crates including stretchind, binding packing of gabion crates with rubble stones all complete | m3 | 525 | 0.2 | 0.39 | 105 | 204.75
| b).Packing and filling of gabion creates with rubble stones |  | 525 | 1.5 | 0.5 | 787.5 | 262.5
9 | Dry Stone Soling Work In Side Drain | m3 | 356.329 | 1 | 0 | 356.329 | 0
10 | Dry stone Causeway | Nos.
| a).Earth work in excavation | m3 | 22.63 | 0.6 | 0 | 13.578 | 0
| b).Dry stone soling | m3 | 13.5 | 2.5 | 0 | 33.75 | 0
| c).Dry stone wall | m3 | 6.36 | 1.5 | 0.5 | 9.54 | 3.18
11 | Floodway construction | Nos. | 1
| a).Earth work in excavation | m3 | 14 | 0.6 | 0 | 8.4 | 0
| b).Boulder packing work | m3 | 20.25 | 2.5 | 0 | 50.625 | 0
c).Gabion wall
| i).Fabrication of gabion boxes including rolling, cutting, assembling of wire crates including stretchind, binding packing of gabion crates with rubble stones all complete | Box | 13 | 0.2 | 0.39 | 2.6 | 5.07
| ii).Packing and filling of gabion creates with rubble stones | m3 | 26 | 1.5 | 0.5 | 39 | 13
12 | scupper culvert construction |  |  | 3.35 | 0 | 0 | 0
| a)E/W in excavation for foundation in hard soil | m3 | 219.375 | 0.6 | 0 | 131.625 | 0
| b)D/S soling at bed | m3 | 45.63 | 1.5 | 0 | 68.445 | 0
| c)D/S masonary wall | m3 | 54 | 1.5 | 0 | 81 | 0
| d)Earth filling | m3 | 48.6 | 0.25 | 0 | 12.15 | 0
13 | Spot gravelling work | m3 | 1238.598 | 3.35 | 0 | 4149.3033 | 0
[5 empty] | Total | 79746.4489 | 1297.37

## labourcalcu-bha
Summary Of Quantity And Labour Calculation
Project : Bagarkot-Bhageswar Green Road
V.D.C : Bhageswar
SN | Description of Works | Unit | Qty. | Labour Per Unit |  | Total MD
|  |  |  | Unskilled | skilled | Unskilled | skilled
1 | Site Clearance Clearing and grubbing including the cutting of trees having girth of less than 30 cm when measured at 1 m above the ground | m2 | 6448.45 | 0.04 | 0 | 257.938 | 0
2 | Cutting of trees: having girth of above 30 cm when measued at 1m above the ground including the removal along the lead route for trees of size:
| i) 30-60 cm girth | No. | 1 | 0.3 | 0 | 0.3 | 0
| ii)60-90 cm girth | No. | 18 | 0.4 | 0 | 7.2 | 0
| iii) 90-180 cm girth | No. | 6 | 1.5 | 0 | 9 | 0
| iv) 180-270 cm girth | No. | 0 | 3 | 0 | 0 | 0
| v) 270-450 cm girth | No. | 0 | 10 | 0 | 0 | 0
3 | Excavation of roadway and drain Including disposal of material up to a lead of 50 m along the lead route
| i) Ordinary soil | m3 | 9314.911 | 0.5 | 0 | 4657.4555 | 0
| ii)Hard soil | m3 | 8305.4951 | 0.6 | 0 | 4983.297 | 0
| iii) Ordinary rock | m3 | 1587.534 | 2 | 0 | 3175.0681 | 0
| iv)Medium rock | m3 | 1631.5325 | 4 | 0 | 6526.1301 | 0
| v)Hard rock requirng chiseling | m3 | 0 | 17 | 0 | 0 | 0
4 | Construction of Roadway embankments and miscellaneous backfilling areas with approved material | m3 | 6370.2437 | 0.25 | 0 | 1592.5609 | 0
5 | Excavation in foundation for structures Including disposal of material up to a lead of 50 m.
| i) Ordinary soil | m3 | 201.8229 | 1 | 0 | 201.8229 | 0
| ii)Hard soil | m3 | 264.387 | 2 | 0 | 528.774 | 0
| iii) Ordinary rock | m3 | 420.5312 | 4 | 0 | 1682.1248 | 0
| iv)Medium rock | m3 | 371.4504 | 8 | 0 | 0 | 0
| v)Hard rock requirng chiseling | m3 | 0 | 30 | 0 | 0 | 0
6 | Dry stone masonary retaining wall work Dry stone wall.(including scafolding) | m3 | 2234.805 | 1.5 | 0.5 | 3352.2075 | 1117.4025
7 | Gabion retaining wall Work a).Fabrication of gabion boxes including rolling, cutting, assembling of wire crates including stretchind, binding packing of gabion crates with rubble stones all complete | Box | 947 | 0.2 | 0.39 | 189.4 | 369.33
| b).Packing and filling of gabion creates with rubble stones | m3 | 473.5 | 1.5 | 0.5 | 710.25 | 236.75
8 | Dry Stone Soling Work
| In Side Drain | m3 | 73.2479 | 1 | 0 | 73.2479 | 0
9 | Dry stone Causeway | Nos.
| a).Earth work in excavation | m3 | 0 | 0.6 | 0 | 0 | 0
| b).Dry stone soling | m3 | 0 | 2.5 | 0 | 0 | 0
| c).Dry stone wall | m3 | 0 | 1.5 | 0.5 | 0 | 0
10 | Floodway construction |  |  |  | 0 | 0 | 0
| a).Earth work in excavation | Nos. | 1 | 0.6 | 0 | 0.6 | 0
| b).Boulder packing work | m3 | 14 | 2.5 | 0 | 35 | 0
c).Gabion wall
| i).Fabrication of gabion boxes including rolling, cutting, assembling of wire crates including stretchind, binding packing of gabion crates with rubble stones all complete | Box | 13 | 0.2 | 0.39 | 2.6 | 5.07
| ii).Packing and filling of gabion creates with rubble stones | m3 | 26 | 1.5 | 0 | 39 | 0
11 | scupper culvert construction |  |  |  | 0 | 0 | 0
| a)E/W in excavation for foundation in hard soil | m3 | 43.875 | 0.6 | 0 | 26.325 | 0
| b)D/S soling at bed | m3 | 9.126 | 1.5 | 0 | 13.689 | 0
| c)D/S masonary wall | m3 | 10.8 | 1.5 | 0 | 16.2 | 0
| d)Earth filling | m3 | 9.72 | 0.25 | 0 | 2.43 | 0
12 | Spot gravelling work | m3 | 954.45 | 3.35 | 0 | 3197.4075 | 0
[5 empty] | Total | 31280.0282 | 1733.6225