- Done

- To Be done…

- Basement Cleanup/Living space shift:

- Move piano/couch to den

- Get rid of piano

- Get rid of couch

- Build dollies for basement storage

- Box junk in basement

- Organize Christmas Decorations

- Dispose of old paint

- Box good paint

- Box books

- Take apart old workbenches

- Build basement utility shelves

- Move utility stuff to shelves

- Throw out old nasty cabinets

- Shift storage cabinets to make more room

- Box table saw

- Dismantle work table and get rid of

- Move living room stuff to storage in basement

- Move family room to living room

- Remove FR carpet

- Move den stuff to basement

- Put ropes on dollies

- Finalize design

- Pre-permit:

- Call HVAC folks for estimate

- Fill-in kitchen pass-through

- Move FR door to hall

- Move hydrangeas

- Remove deck railings

- Remove FR siding/windows/doors

- Remove deck

- Remove rear gutters

- Remove rear siding

- Install rear insulation/ply/Tyvec

- Get permit

- To do before construction:

- Install new Electric service

- Mill Erler's Walnut log

- Mail electric info to Frank

- Meet with Dan and HVAC

- Remove FR floor

- Clean up lumber in back

- Build cart

- Move potted plants to back

- Move firewood to Tom's yard

- Remove side fence

- Move in-ground plants that may be in the way of a bobcat

- Flag plants for do-not-disturb

- Install temporary railings for basement entry

- Remove exterior fence lighting

- Move side deck to rear/front?

- Order materials

- Footer Inspection

- Initial Exterior construction

- Install HVAC (C)

- Build floor structure (C)

- Insulate/HVAC ducts (C/me/HVAC)

- Floor Close-in Inspection

- During Construction: (preparing for Close-in inspection)

- Move delivered materials to rear

- Move delivered trusses to rear

- Install new wall Tyvec

- Install Windows ©

- Install back Door ©

- Clean out Den for new wall construction

- Punch out ceiling and install cross braces if necessary

- Remove Den trim

- Build temp door

- Remove bad outlet below pass-through

- Install new roof

- Main roof felt

- Gable roof felt

- Purchase flashing

- Purchase vents

Purchase shingles

Install flashing

Install edging

Install shingles

Install vents

Cut holes for vents in soffit

Install little vents under soffit

Purchase Frieze

Install Frieze

Paint facia/Soffit/Frieze

Tiny BR

Remove mirror

Reframe mirror

Install mirror

Add flex hose for fan? (replace fan?)

Repair plaster

Paint

Install Electrical (me and C)

Purchase Frank’s materials list

Purchase outdoor light fixtures

Purchase inside fans

Redo kitchen electrical

Cleanup basement electrical (me and C)

Install FR switch boxes

Install FR outlet boxes

Install FR Fan box

Install FR cable

Install FR network cable

Install FR phone cable

Install MBR switch boxes

Install MBR outlet boxes

Install MBR Fan box

Install MBR cable

Install MBR network cable

Install MBR phone cable

Install MBath switch boxes

Install MBath outlet boxes

Install Mbath fan

Install Mbath light boxes

Install Plumbing (C)

Install new waterheater (C)

Close-in inspection

Electrical

Plumbing

Framing

Insulate FR

Insulate FR Ceiling

Insulate master bedroom

Insulate master bedroom ceiling

# Insulation Inspection

Install wallboard

Install glass block in upstairs BR (C?)

Install new tile for bathroom under window (C?)

Repair upstairs bath plaster

Install 2nd floor rear windows

Finish inside walls of second floor rear wall

Purchase MBR fixtures

Mirror

Toilet

Shower fixtures

Vanity(s)

Install water spigot for North side out of basement

Porch

Purchase Trim

Purchase poles/railings

Install Poles

Install base trim

Paint base trim

Install Decking

Install trim

Purchase Ceiling

Install ceiling

Paint trim

Old Siding

Purchase ½” ply

N

Remove siding

Re-route Upstairs BR power

Re-route Upstairs BR phone line

Re-route main cable

Insulate

Ply

Tyvec

Install new windows

Install window trim

Install siding

W

Remove siding

Install plugs under front windows interior

Insulate

Ply

Tyvec

Install new windows

Install window trim

Install siding

S

Remove siding

Install plugs under front windows interior

Insulate

Ply

Tyvec

Install new windows

Install window trim

Install siding

Front Dormers

Remove siding

Insulate

Ply

Install overhang ladders

Tyvec

Install new windows

Install window trim

Install siding

Second Floor Rear

Install new windows

Install window trim

Install siding

Old Roof

Install N ladder

Install S ladder

Install E overhang

Install W overhang

Install Frieze boards

Install Facias/soffits

Remove old roofing

Remove Chimney to be below 2nd floor ceiling

Replace bad wood

Secure overhang boards from above with another screw or two

Install new felt

Install new flashing

Install edging

Install Shingles

Install gutters

Master Bathroom

Tile (C)

Install fixtures (C)

Exterior finishing:

Siding (C)

Gutters (C)

Light fixtures

Outside wall plugs

Wall finishing:

Install wall board

Paint walls

Install electrical outlet covers/Ceiling fans

Prime trim if unprimed

Install trim

Paint Trim

Install closet/MBR doors

Final finishing

Install wood floor/finish/let dry for one week (C?)

Install floor trim

Final Inspection

Remove rest of chimney (C)

New Hall Closet

Frame new walls

Finish walls

Install door

Install shelves

Pre Move-in

Buy area rug family room

Buy TV/Entertainment center

Buy shelving system(s) for MBR closets(s)

Install window treatments

Post construction:

Install water for rear out of basement

Strip hall doors/trim

Fix doorknobs in hall*

Build playroom walls

Buy 9x12 playroom carpet

Fix-up rear fencing*

Build linen closet in upstairs hall*

Replace basement stairs*

* can be done anytime

C - to be done by contractor