## Sheet1
SWE 626 Project Plan - Team 1
Task Name |  | Start Date | End Date | Task Lead | Task 2nd Lead | Task Members | % Completed
Software Requirement Specification - Throwaway Prototypes |  |  | 2002-02-13
1.a Software Requirement Specification |  | 2002-02-01 | 2002-02-04 | Peter | Sandra |  | 100%
Prototype - Multiple Document Interface |  | 2002-02-04 | 2002-02-12 | Pradeep |  |  | 100%
Prototype - Reservation Interface |  | 2002-02-04 | 2002-02-12 | Pradeep |  |  | 100%
Requirements model
1.b | Use case model | 2002-02-04 | 2002-02-11 | Susan | Reita | Kai, Peter, Sandra | 100%
1.c | System context model | 2002-02-11 | 2002-02-12 | Kai |  |  | 100%
Analysis and Design Model |  |  | 2002-03-13
Analysis Model
2.a | Static model | 2002-02-14 | 2002-02-25 | Reita |  |  | 100%
2.b | Statecharts | 2002-02-14 | 2002-02-25 | Peter | Sandra |  | 100%
2.c | Interaction diagrams | 2002-02-14 | 2002-02-25 | Kai | Susan | Reita, Pradeep, Sandra, Peter | 100%
2.d | Message sequence descriptions | 2002-02-25 | 2002-02-28 | Susan | Kai |  | 100%
Design Model
3.a | Consolidated set of colloboration diagrams | 2002-02-28 | 2002-03-04 | Kai | Susan |  | 100%
3.b.I | Description of how system is decomposed into component-based subsystems | 2002-02-25 | 2002-03-04 | Sandra | Pradeep |  | 100%
3.b.ii | Design of Relational Database | 2002-02-27 | 2002-03-04 | Pradeep | Reita | everyone | 100%
3.c.I | Overview of desc of the subsystem software architecture | 2002-02-25 | 2002-03-04 | Peter | Sandra
3.c.ii | Task architecture | 2002-02-25 | 2002-03-04 | Peter | Reita |  | 100%
3.c.iii | Description of information hiding classes | 2002-02-25 | 2002-03-04 | Reita | Peter |  | 100%
Application |  |  | 2002-04-24
| Code Checkin Screen |  |  | Reita
| Code Room Screen |  |  | Reita
| Code Customer Record Screen |  |  | Reita
| Code Checkout Screen |  |  | Reita
| Code Hotel Payment & Bill Screen |  |  | Kai
| Code Administer Rooms Screen |  |  | Susan
| Code Administer User Screen |  |  | Susan
| Code Report Screen |  |  | Peter
| Code Scheduler Class |  |  | Pradeep
| Code Reservation Screen |  |  | Pradeep
| Code Parent MDI |  |  | Pradeep
| Code Database/CLIENT (Utilities) Class |  |  | Pradeep
| Code Login Screen |  |  | Pradeep
| Develop and Maintain Database |  |  | Pradeep | everyone
4. Software Implementation description |  |  |  | Sandra
5. Detailed test specification |  |  |  | Susan | Sandra
6. Working system code documentation - tested using test specification |  |  |  | everyone | everyone
Unit Testing Report |  |  | 2002-04-20
| Create unit testing plans |  |  | Sandra | Kai
| Execute unit test plan |  |  | Kai | Susan
| Unit Testing Report |  |  | Sandra
Integration Testing Report |  |  | 2002-04-21
| Create integration testing plan |  |  | Sandra | Susan
| Execute integration testing plans |  |  | Kai | Susan
| Integration Testing Report |  |  | Sandra
System Testing Report |  |  | 2002-05-08
| System Testing for Library System |  |  | Kai
| Obtain the library system software developed by Team 2 |  |  | Sandra
| Create system testing plan |  |  | Sandra
| Execute system testing plan |  |  | Sandra | Kai
| System Testing Report |  |  | Sandra | Kai
Project Management
| Work breakdown schedule | 2002-02-11 | 2002-02-15 | Sandra |  |  | 100%
| Project schedule | 2002-02-01 | ongoing | Reita | Sandra |  | 100%
| Software development plan | 2002-02-18 | 2002-02-25 | Reita | Sandra |  | 100%
| Software implementation plan | 2002-02-11 | 2002-02-15 | Sandra |  |  | 100%
| Software test plan | 2002-02-11 | 2002-02-15 | Sandra |  |  | 100%
| Individual project log | 2002-02-01 | ongoing | everyone | everyone |  | ongoing
| Project post-mortem | end of project | end of project | everyone | everyone
Presentations
| 2002-02-13 | Sandra, Peter, Pradeep
| 2002-03-20 | Kai, Reita, Susan
2002-04-17
2002-05-08
2nd Presentation
| Static model | Reita
| Statecharts | Susan
| Consolidated set of colloboration diagrams | Susan
| Description of how system is decomposed into component-based subsystems | Kai
| Design of Relational Database | Reita
| Overview of desc of the subsystem software architecture | Kai
| Task architecture | Kai
| Description of information hiding classes | Reita