## Sheet2
Date | Activity
2003-01-22 | Group formation to develop the Student Tracking and Admission System (SATS)
2003-01-25 | First Meeting to discuss the problem statement
Update the group website for Project documents
2003-01-27 | Study problem statement, Analyse use casees from the existing use cases diagrams and use case descriptions.
2003-01-29 | Created use case diagrams
2003-02-02 | Dissussed use case diagrams with the team and modified them according to the discussions and suggestions in the team meeting
2003-02-03 | Divided and assign the work of use case description among group members
Working on Use case discriptions
Making changes to Use case diagrams as necessary
2003-02-08 | Continue Working on Use case discriptions,
Checking the integrated use case description for formatting
Work with Kim on Work Break Down Structure
2003-02-23 | Evaluated prototype and propose suggestions
Working on Entity entity class diagrams
2003-03-09 | Applying templates to the prototype
Install dreamweaver tool to prepare for creating HTML forms
Learning Dreamweaver tool and creating HTML forms for the project.
2003-03-15 | Divide and assign the work of collaboration diagrams and state chart among team members
Work on collaboration diagrams
Worked on state chart diagrams
Work on message sequence descriptions
2003-03-19 | SATS database
Work with Joan and Kim to create SATS database
Modify and Finalize Static Model/Entity Class Diagram
2003-03-24 | Divide and assign the work of creating HTML form among team member
Modify form template to make it easy to change
Working on HTML form
2003-03-30 | Working on forms and database
Continue to work on HTML forms
Update attributes in database tables
Setup relation between tables and contrains
2003-04-06 | Continue working on forms and database
Continue to update forms and database following Anurag coding
2003-04-13 | Perform unit test
modify collaboration diagrams for presentation
Work with Anurag and Vasudha to perform unit testing and have suggestion
Prepare slides for presentation
Presentation
2003-04-20 | Continue working on unit test
Modify database, and forms to match fields and attributes
2003-04-27 | Working on system testing
Modify database, and forms to match fields and attributes
2003-05-04 | Working on forms, database
Help with Sytem test plan
Help with Sytem integration plan
Work with Anurag/Vasuhda on Integration test report

## Sheet1
Date | Activities
2002-01-23 | We formed as a challenging group to develop Student Tracking and Admission System (SATS)
2002-01-28 | Discussed provisional plans about SRS and Prototype development of SATS
Discussed adopting technology to develop SATS
2002-01-30 | Participated in a group to review SON on the Library Management System and discussed concerns with the SON.
Distributed work among individuals in the team to start working on SRS, Use Cases and Prototype for Library Management System.
2002-02-03 | Developed Screens for User
2002-02-04 | Presented screens developed to team and noted suggestions given by team members to update.
Discussed on SRS and Use Cases and Reports.
Discussed concerrns on SON of Hotel Management System and Library Management System.
2002-02-06 | Updating member interactive Screens.
2002-02-11 | Reviewed Use Cases and SRS and made some suggestions.
Given a demo on prototype and noted suggestions by other team members to update member interactive screens.
2002-02-12 | Updated member interface section of the prototype.
Contributed in development of tracebilitymatrix.
2002-02-19 | Met with group to discuss static class diagram and discussed changes.
2002-02-21 | Updating prototype.
2002-02-25 | Participated in a group discussion to modify static model. Discussed on Collaboration diagrams and state charts. Distributed work load in developing Collaboration diagrams and state charts. Discussed on Objects at design level.
2002-03-01 | Updated Prototype. Developed Collaboration diagrams. Met with group and Reviewed sample Collaboration diagrams. Noted comments for changes.
2002-03-04 | Met with team and reviewed updated collaboration diagrams and noted comments.
2002-03-05 | Met with team and reviewed updated collaboration diagrams and started working on message sequence descriptions.
2002-03-06 | Started working on description of Information hiding classes.
2002-03-09 | Met with group and reviewed collaboration diagrams and working on Information hiding classes. Reviewed static model, data dictionary and database design.
2002-03-19 | Met with group to review deliverables due on 03/20/02.
2002-03-20 | Met with group and reviewed draft. Presented collaboration diagrams to the class.
2002-03-26 | Met with the group to discuss test cases.
2002-04-08 | Met with group and discussed assignments and reviewed. Met with Dr.Wu.
2002-04-09 | Working on test cases for Inventory.
2002-04-15 | Met with group and reviewed project progress and got feed back for Inventory test cases.
2002-04-20 | Completed test cases and submitted to team.
2002-04-29 | Met with group and reviewed project progress and discussed on System testing.
2002-05-01 | Met with group and participated in installing system to the client and participated in demo of Hotel Management System given by our Developers.
2002-05-06 | Met with group to discuss final presentation and issues related.