### Online Health and Nutrition Management Information System

[Make following changes in the figure: Add a box Like the box ‘Epidemiological software’ above Dev Info and use the phrase ‘Standard Mapping software’ and put Arc Info above Dev Info [Put a footnote “Retrieval access only”]. Instead of the term ‘Native Spatial analysis tool’ use ‘Customised Mapping Tool’]

The development of and Online Health and Nutrition Management Information System will comprise of the following components:

Online Data Processing:

It will be possible for staff based in Island Health Posts / Health Centres / Family Health Units to directly enter child level data to a web-based centralized system based in Malé (Do not commit right now). Simple customized screen will be developed in Dhivehi to enter this data.

Feedback Modules:

Online feedback modules for Atoll / Regional Hospitals and Island Health Posts / Health Centres / Family Health Units will be available, for reporting, monitoring and self assessment to all management levels.

Native analysis tools:

Native analytical tools for quantitative reporting and analysis and spatial analysis will be developed as part of systems implementation for ongoing Health and Nutritional status monitoring and reporting.

Third party tools:

Specialized tools for indicator monitoring and mapping, for example, DevInfo and ArcInfo; tools for statistical analysis, for example, SPSS or STATA; tools for epidemiological analysis, for example, EPI Info; Advanced spatial analysis, for example [Drop],; will be available to utilize data from the Online Health and Nutritional database, [through retrieval access] for in-depth analysis and monitoring.

2.3 Tentative time schedule

A tentative time schedule for the entire project is given in the following table

|  | Months |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activity | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |
| Brain storming session before FRS |  |  |  |  |  |  |  |  |  |  |  |  |
| System Requirements Report Preparation |  |  |  |  |  |  |  |  |  |  |  |  |
| Approval of System Requirement |  |  |  |  |  |  |  |  |  |  |  |  |
| System Design Document (SDD) |  |  |  |  |  |  |  |  |  |  |  |  |
| Approval of System Design Document |  |  |  |  |  |  |  |  |  |  |  |  |
| Developing the System |  |  |  |  |  |  |  |  |  |  |  |  |
| Testing the System |  |  |  |  |  |  |  |  |  |  |  |  |
| Running the System parallely with existing system |  |  |  |  |  |  |  |  |  |  |  |  |
| Capacity building for Island level, Atoll level and Central level. |  |  |  |  |  |  |  |  |  |  |  |  |
| Hand Over |  |  |  |  |  |  |  |  |  |  |  |  |

Note: The above schedule is tentative as this can be finalized after the brainstorming session.

2.4 Details of activity

| Activity | Expected Outcome |
| --- | --- |
| Brain storming session before FRS | Finalising all policy related issues Selecting Nodal Persons of MOH Data requirement and cohort register Revised MIS Framework Technical feasibility Software requirement specification Decision about Server Location/s Decision on Capacity Building Issues Finalisation and approvals of time-schedule of receivables, deliverables and milestones |
| Systems Requirement Report (SRR) | Hardware Sizing (specifications and quantity of computers, servers, peripherals, Network need) Software Specification Overall system Architecture Data Flow Structure Database Structure Input , Output Requirements Data Capturing and Master-file creation Methodology(from legacy data, Newly identified data) Fixing of Implementation plan Implementation methodology Training need analysis(User of operator level and managerial level, Administration level, Technical level) Training Plan Back-up Strategy Audit Trail Access control and security Testing & Acceptance Methodology |
| Approval of System Requirement | Approval of the SRR |
| System Design Document(SDD) | Detail Design of Database Table Design of Input and output screens Defining relations between different modules Detail design of Access control and security |
| Approval of System Design Document | Approval of the SDD |
| Developing the System | Development of Prototype |
| Testing the System | With test data and with live data, Installing and configuring on-site, test run. |
| Running the System parallel to existing system | Running the System |
| Capacity building for Island level, Atoll level and Central level. | Smooth data flow, Regular Data analysis and Two-way feed-back system in place |
| Hand Over | Handing over of the system |