To

The Chairman NOC

Room No. 306 Vigyan Sadan,

R k Puram, Sector 10 –New Delhi

Sub; Progress Report YSA2004- SOC Punjab- Consolidated Report

Sir

As already informed vide letters dated17-2-04, 23-2-04, 26-2-04,4-3-04,5-3-04 on the subject cited above I have the pleasure to inform that ROC NORTH CENTRAL REGION Mrs Neelam Gulati Sharma held two meetings to constitute SOC for Punjab. In the second meeting held at Punjab Agriculture University Ludhiana on 11-7-03 the SOC was constituted when in a very well attended meeting of 13 NGOs, BHARAT GYAN VIGYAN SAMITHI was selected as the SCA and ITS state Coordinator Dr, P. L. Garg was elected the State Coordinator for YSA2004. After this the SOC held meetings on 11-07-03at Ludhiana itself and resolved that the constituent organizations and others shall prepare draft project reports soon. It was also decided that a meeting cum training shall be held at Chandigarh in Dr. Anuj Sinha will be requested to impart training on project formulation.

For finalization of draft project of NGOs. The SOC Coordinator and ROC Coordinator held 15 meetings on 19-8-03, 27-08-03, 18-09-03, 25-09-03, 29-09-03, 28-10-03, 6-11-03, 27-11-03, 17-12-03, 19-12-03, 21-12-03, 23-12-03, 6-01-04, 5-02-04 and 9-02-04.

A Regional meeting was also held on 6-08-03 at Chandigarh in which SOC Punjab members participated in good number and the meeting worked like a training workshop. Dr.Anuj Sinha imparted training on themes of YSA2004 and the guidelines to prepare the projects.

SOC also held meetings on 6-1-04 to discuss the projects of various NGOs in light new guidelines on budget. All the NGOs were called to discuss their projects and a brief of the projects was submitted to ROC, a copy of which was sent to each NGO for information.

BGVS and SOC office also started preparing the soft ware and selecting the same out of existing one and building the organizing of YSA2004.DOCs constituted are enclosed as list, the details were presented in the NOC meeting held at Chandigarh on 13 and 14 Feb.

The activities done after NOC meeting have been reported from time to time however a brief is given as under

1 Material Procurement:- Materials on the selected themes of water and sanitation, health and nutrition, biodiversity, disaster management and soil conservation along with the role of information technology in right to information has been procured.

2 a) Transcription of material in local language;- the available from NCSTC and BGVS on kala jatha  has been translated in Punjabi by translation expert Dr. Paramjeet Singh .

b) The folder issued by NOC has been translated, wetted and made ready for printing in Punjabi and 1600 copies have been prepared on rota.

c) The material on health and Science Awareness is ready for printing as per list attached

d) Material on biodiversity has been transcribed in Punjabi and hand written script is being wetted.

e) Disaster management material has been modified as per disaster problems faced by Punjab in past 30-40 years particularly floods.

3) Duplication of material; Introductory folder issued by NOC in English has been duplicated and out of 1600 copies prepared more than 1000 have been circulated/distributed to the SOC member organizations and DOCs., for use on Launching of YSA 2004 on NSD the 28th Feb. 2004.

Launching of YSA 2004 on NSD as declared in NOC meeting, All the member organizations were encouraged to launch YSA on NSD to which there was a big response and as a result YSA was launched at about 100 places out of which at about 80 places it was launched on 28 Feb. 2004 by BGVS mainly and two other org. participating in non jatha activities from Sangrur and Hoshiarpur have sent the report of launching of YSA-04 on NSD. Director Science Education has issued a letter for launching of YSA on NSD to all the District Education Officers in the state on request of SCA. Reports are being collected. The activity is going on still at certain places. Reports are pouring in. At a few places despite the annual examinations a novel way to launch was that the students of various Schools were gathered and a lecture was delivered by center Superintendents on the importance and themes and programmes of YSA2004.

b) Science Teachers of district Sangrur have decided that they will install a Board in each of the 300 Senior Secondary and High Schools of the district designated as YSA2004 with the insignia of YSA2004 on it. The teacher in charge of the board shall encourage the other teachers and students to write new information about the themes of YSA2004.

c) Another feature of this campaign has been that a large No. of  Neoliterates Volunteers of literacy and members of self help groups have been involved in YSA activities.

d) At Hoshiarpur undersigned on March 8 motivated the gathering of about 600 women activists of literacy movement to work on the themes of YSA2004 and direct their fortnightly awareness activities to the Science Awareness and the material on infant feeding was displayed by BGVS. The district Coordinator and the block coordinators assured of their efforts on the issue and the Chief Guest Smt. Sukhwant Kaur Bhuller the Chairperson of social health, wife of the Deputy Commissioner also assured all kind of support to the YSA2004.

d) DOC Sangrur has suggested that a calendar of YSA 2004 bearing portraits of INDIAN SCIENTISTS be issued which may be placed in each school to create long term effect of YSA2004 and encourage the students towards Scientific Thinking.

ORGANISATION:-    after the NOC meeting  SCA has been able to constitute DOC in Kapurthala and training of district team hase been conducted by state coordinator. The DOC is going to hold a seminar of Science Teachers in next month on themes of YSA

100 spots for kala jatha have been identified and 300 surounding spots for year long activity have also been identified.

The letter head has been finalized and is under print. Sh. N. S. Rattan IAS retired has agreed to be the patron of SOC. The list of advisory committee has also been finalized and a request letter is going to be sent to each of the dignitaries for acceptance.

Sincerely Yours

P. L. Garg

Copy to Coordinator ROC

DOCs:_ DOCs. Have been constituted in following districts

Ferzepur, Faridkot, Moga , Sangrur, Ludhiana, Ropar, Nawan Shehar, Hoshiarpur Mukatsar.

More than one contact person have been identified in Patiala , Batinda, Gurdaspur Jallandher and Amritsar. Process is on.

# Loc’s: About 100 spots for Loc’s have been identified.

LIST OF BOOKS

Following books are to be reprinted / printed for first time as soft ware

A)Health:- How does the human embryo develop

1  Imagical morning

2  Save children from diarhoea

3 Why do children become malnutrite

4 Water born diseases

5 Breast feed the infant

6 Coughs and cold

7 Immunisation when and why

8 Before the coming of new arrival

9 We can choose

10 From darkness to light

11 Mental health series- like Symptos of body Diseases of Mind

12 All about Intoxicants

13 Infant feeding—1

14 Food Adultration

16 Infant feeding--2

17 Women Health Series

# B) SCIENCE AWARENESS

1 Tap bhap and you

2 Vigyan de pryog

3 Akh de kahani

4 Solar eclipse

5 Khed khed vich siksha

6 Sadako ate kagaj de panchhi

7 Egg to chicken

8 Sacha sathi neem

9 Sada pata(Our address)

10 What is science

11 Kura karkat

12 Safai- kura karkat to kamai(Earning from waste)

13 Ball Geet Series

14 Let us plant trees

15  Khed Khed Vich Vigyan

16 Nawan savera

17 Science in Kitchen

18 Explaining Miracles

19 Learning by Doing

20 Paper folding

C) WATER RELAT ED

1 Dried up well

2 Not a drop to waste

3 Water cycle

4 Water born diseases(under health also)

# D) SOIL AND COVER MANAGEMENT

1 My land does not yield

2 Success story

3 How to use pesticide safely

4 Towards integerated pest management

5 Experiments in our backyard

6 Our common heritage

# E)DISASTER preparedness

1 Scope and preparedness for disaster

F)BIODIVERSITY-what it is and what is the need to preserve it

A total of more than 40 books have been selected/prepared